## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Keshiary | Central Drilling | DUDHE BUDE AND ADJOINING MOUJAS PWSS | SM/13080 | New | Providing drilling crew and other works for construction of Tube Well (250 mm X 150 mm x 220 Mtrs. Depth) by utilising Departmental Machineries for Dudhe Bude W/S Scheme (T/W-I & II), Keshiery Block under Paschim Medinipur Distrct, CDD PHE Dte. | Driller In Charge | Junior Engineer | ORD/000059/2023-2024 | 392/CDD | 18/05/2023 | 17/06/2023 | SUNRISE ENGINEERING CORPORATION | 25.42 | 0 | 0 | 100
2 | PASCHIM MEDINIPUR | Keshiary | Midnapore Division | DUDHE BUDE AND ADJOINING MOUJAS PWSS | SM/13080 | New | Material Requisition To Resource Division |  |  | RTOR000119/2023-2024 | 1311/MD | 28/04/2023 | 28/04/2023 | Resource Division | 30.52 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | DUDHE BUDE AND ADJOINING MOUJAS PWSS | SM/13080 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for DUDHE BUDE AND ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001448/2023-2024 | 3081/W/MMD | 29/11/2023 | 27/05/2024 | SANKAR PRASAD DUTTA AND CO | 22.99 | 0 | 0 | 30
4 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | DUDHE BUDE AND ADJOINING MOUJAS PWSS | SM/13080 | New | Electric quotation bill for Tw No-I of Dudhebudhe PWSS. (Ref Consumer ID-204136081) |  |  | BILL/02992/2023-2024 | BP-2023-24-384 | 02/12/2023 | 02/12/2023 | WBSEDCL | 4.06 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | DUDHE BUDE AND ADJOINING MOUJAS PWSS | SM/13080 | New | Electric quotation bill for Tw No-II of Dudhebudhe PWSS. (Ref Consumer ID-204136079) |  |  | BILL/02993/2023-2024 | BP-2023-24-383 | 02/12/2023 | 02/12/2023 | WBSEDCL | 2.91 | 0 | 0 | 0
Total | [13 empty] | 85.9 | 0 | 0