## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | ELUNI PIPED WATER SUPPLY SCHEME | SM/13081 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for ELUNI PIPED WATER SUPPLY SCHEME under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001618/2022-2023 | 535/W/MMD | 20/03/2023 | 31/05/2025 | DEBJYOTI BASU | 22.78 | 14.24 | 62.5 | 25
2 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | ELUNI PIPED WATER SUPPLY SCHEME | SM/13081 | New | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including Sub-Soil investigation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (16,427 Nos.) for GAMARIA, UTTAR PIASHALA, KHAS JANGAL, ELUNI, GOPAL BANDH, JHETA JAMBONI, KUBIR CHAK & KUSUMDAHARI Pipe Water Supply Scheme within Keshpur Block under Midnapore Sadar Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | ORD/000183/2023-2024 | 2735/MD | 01/08/2023 | 07/04/2026 | M/S. S.S. ENTERPRISE | 5732.3 | 209.04 | 3.65 | 75
3 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | ELUNI PIPED WATER SUPPLY SCHEME | SM/13081 | New | Material Requisition To Resource Division |  |  | RTOR000049/2024-2025 | 3369/MD | 25/11/2024 | 25/11/2024 | Resource Division | 10.82 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | ELUNI PIPED WATER SUPPLY SCHEME | SM/13081 | New | Electric quotation bill for Tw No-I of ELUNI PWSS. (Ref Consumer ID-204188708), APPLICATION NO-2004550744, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-UPPERKUAI CCC |  |  | BILL/03550/2023-2024 | BP-2023-24-616 | 07/02/2024 | 07/02/2024 | WBSEDCL | 2.88 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | ELUNI PIPED WATER SUPPLY SCHEME | SM/13081 | New | Electric quotation bill for Tw No-II of ELUNI PWSS. (Ref Consumer ID-204200310), Application No-2004571268, Application Type-New Connection, Name of CCC-Upperkuai. Block-Keshpur |  |  | BILL/03542/2023-2024 | BP-2023-24-617 | 07/02/2024 | 07/02/2024 | WBSEDCL | 3.19 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | ELUNI PIPED WATER SUPPLY SCHEME | SM/13081 | New | Laying of rising main & interconnection for Eluni & its adjoining mouzas PWSS, Block ¿ Keshpur, District ¿ Paschim Medinipur under Midnapore Division, PHE Dte. (Length = 1,040 Mtr.). | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | ORD/000376/2024-2025 | 51/MD | 07/01/2025 | 21/02/2025 | SAYEEDI CONSTRUCTION | 6.84 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | ELUNI PIPED WATER SUPPLY SCHEME | SM/13081 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different ongoing piped water supply scheme for covering Midnapore Sadar Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.- w.e.f.-01-07-2025 to 28-02-2026 (Vehicle No. WB33C 6546) | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000513/2025-2026 | 842/MMSD-I | 11/06/2025 | 09/02/2026 | M/S BIKASH DE | 3.66 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | ELUNI PIPED WATER SUPPLY SCHEME | SM/13081 | New | NAME OF WORK - ADDITIONAL QUOTATION FOR SHIFTING OF 25 KVA DTR CURRENTLY INSTALLED AT ELUNI PWSS, REFERENCE ID- 860334533, APPLICATION ID- 100000136963, NAME OF CCC- UPPERKUAI CCC, NAME OF BLOCK- KESHPUR, APPLICATION TYPE- DEPOSIT WORKS OTHER THAN SERVICE CONNECTION. |  |  | BILL/00722/2025-2026 | 42156 | 07/08/2025 | 07/08/2025 | WBSEDCL | 1.35 | 0 | 0 | 0
Total | [13 empty] | 5783.82 | 223.28 | 3.86