## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | GAMA AND ADJOINING MOUJAS PWSS | SM/13083 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Narayangarh Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- (1) Raipur (JL.- 452, Plot-926), (2) Asti (JL.- 706, Plot-496/850), (3) Babalpur (JL.- 350, Plot-876/906), (4) Bahurupa (JL.- 268, Plot-2137), (5) Barakalanki (JL.- 508, Plot-838/1168), (6) Bargopal (JL.- 480, Plot-228/620), (7) Duria (JL.- 583, Plot-686/1639), (8) Gahira (JL.- 727, Plot-1275/1539), (9) Gama (JL.- 545, Plot-532), (10) Govindapur Brahman Saran (JL.- 254, Plot-531/538), (11) Jamuna (JL.- 223, Plot-203), (12) Khursi (JL.- 601, Plot-701/942), (13) Pakurseni (JL.- 520, Plot-608/687), (14) Shuja (JL.- 403, Plot-111/751) & (15) Tutranga (JL.- 671, Plot-897) | AE/RWS Midnapore Sub Division |  | ORD/000597/2022-2023 | 396/MD | 02/02/2023 | 03/05/2023 | JADAVPUR UNIVERSITY | 71.69 | 4.78 | 6.67 | 94
2 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | GAMA AND ADJOINING MOUJAS PWSS | SM/13083 | New | Material Requisition To Resource Division |  |  | RTOR000095/2022-2023 | 184/MD | 16/01/2023 | 16/01/2023 | Resource Division | 14.27 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | GAMA AND ADJOINING MOUJAS PWSS | SM/13083 | New | Material Requisition To Resource Division |  |  | RTOR000113/2024-2025 | 3449/MD | 25/11/2024 | 25/11/2024 | Resource Division | 12.04 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Mechanical | GAMA AND ADJOINING MOUJAS PWSS | SM/13083 | New | Quotation for new power connection at gama PWSS T/W - I under Narayangarh block , application no - 2004739405 , ref no - 204309707 |  |  | BILL/01123/2024-2025 | BP-2024-25-232 | 04/06/2024 | 04/06/2024 | WBSEDCL | 3.32 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Mechanical | GAMA AND ADJOINING MOUJAS PWSS | SM/13083 | New | Quotation for new power connection at gama PWSS T/W - II under Narayangarh block , application no - 2004739453 , ref no - 204309708 |  |  | BILL/01078/2024-2025 | BP-2024-25-231 | 04/06/2024 | 04/06/2024 | WBSEDCL | 3.54 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Mechanical | GAMA AND ADJOINING MOUJAS PWSS | SM/13083 | New | Supply delivery and installation of kit kat fuse carrier for different water supply scheme under Narayangarh Block and others under Midnapore Mechanical Sub Division-I,P.H.E.Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division | ORD/000368/2024-2025 | 1087/MMSD-I | 06/08/2024 | 21/08/2024 | SOUMEN ELECTRIC | 6.62 | 0 | 0 | 50
7 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | GAMA AND ADJOINING MOUJAS PWSS | SM/13083 | New | Continuation Work Order for "Hiring of 1 (One) Motor Cab (Standard) commercial with Catalytic Converter attachment with Bharat Stage as per prevalent application standard compliant new/not older than 30 (thirty) months from the date of 1st registration on daily hire rate basis for 06 (Six) months only having contract carriage permit for plying within West Bengal from the Regional Transport Authority for the use of the Assistant Engineer (H/Q), Midnapore Division, P.H.E. Dte. for the period of 05 (Five) months from 01.06.2025 to 31.10.2025." | Assistant Engineer (HQ) | Junior Engineer (estimating section) | ORD/000218/2025-2026 | 1231/AE/HQ/MD | 27/05/2025 | 24/10/2025 | NAFISA ENTERPRISE | 0.71 | 0 | 0 | 0
Total | [13 empty] | 112.19 | 4.78 | 4.26