## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Dantan-II | Midnapore Division | JAHALDA AND IT'S ADJOINING MOUJAS PWSS | SM/13086 | New | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division |  | ORD/000531/2022-2023 | 2192/MD | 01/11/2022 | 30/01/2023 | JADAVPUR UNIVERSITY | 100.36 | 4.78 | 4.76 | 90
2 | PASCHIM MEDINIPUR | Dantan-II | Central Drilling | JAHALDA AND IT'S ADJOINING MOUJAS PWSS | SM/13086 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 12 | 0.06 | 11
3 | PASCHIM MEDINIPUR | Dantan-II | Midnapore Division | JAHALDA AND IT'S ADJOINING MOUJAS PWSS | SM/13086 | New | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including Sub-Soil investigation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (72023 Nos.) for 41 Nos. PWSS within DANTAN-I, DANTANII & KESHIARY Block Pipe Water Supply Scheme under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II),JE RWS Kharagpur Sub-Division( Keshiary),JE RWS Midnapur Sub-Division( Dantan-I),JE2 Kharagpur Sub Division | ORD/000277/2023-2024 | 5056/MD | 26/10/2023 | 30/06/2026 | ENGINEERING PROJECTS (INDIA) LIMITED | 18003.47 | 16.5 | 0.09 | 30
4 | PASCHIM MEDINIPUR | Dantan-II | Midnapore Division | JAHALDA AND IT'S ADJOINING MOUJAS PWSS | SM/13086 | New | Material Requisition To Resource Division |  |  | RTOR000098/2023-2024 | 1287/MD | 28/04/2023 | 28/04/2023 | Resource Division | 24.63 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Dantan-II | Midnapore Division | JAHALDA AND IT'S ADJOINING MOUJAS PWSS | SM/13086 | New | ELECTRIC QUOTATION BILL FOR TW NO-I OF JAHALDA PWSS. REF CONSUMER ID-204373753, APPLICATION NO-2004852919, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II |  |  | BILL/00447/2024-2025 | BP-2024-25-294 | 27/08/2024 | 27/08/2024 | WBSEDCL | 13.22 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Dantan-II | Midnapore Division | JAHALDA AND IT'S ADJOINING MOUJAS PWSS | SM/13086 | New | ELECTRIC QUOTATION BILL FOR TW NO-II OF JAHALDA PWSS. REF CONSUMER ID-204373747, APPLICATION NO-2004852930, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II |  |  | BILL/00449/2024-2025 | BP-2024-25-294 | 27/08/2024 | 27/08/2024 | WBSEDCL | 9.12 | 0 | 0 | 0
Total | [13 empty] | 39490.56 | 33.28 | 0.08