## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Debra | Midnapore Division | JALIMANDA AND IT'S ADJOINING MOUJAS PWSS | SM/13087 | New | Material Requisition To Resource Division |  |  | RTOR000239/2023-2024 | 1520/MD | 12/05/2023 | 12/05/2023 | Resource Division | 29.35 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | JALIMANDA AND IT'S ADJOINING MOUJAS PWSS | SM/13087 | New | Electrict quotation bill for TW-I of Jalimanda pwss (Ref Consumar ID-204444967),Application No-2004963152,Application Type-New Connection,Name of ccc-Balaichak ccc, block-Debra |  |  | BILL/03029/2024-2025 | C112429710144 | 25/11/2024 | 25/11/2024 | WBSEDCL | 4.15 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | JALIMANDA AND IT'S ADJOINING MOUJAS PWSS | SM/13087 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for JALIMANDA AND IT'S ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001655/2022-2023 | 576/W/MMD | 20/03/2023 | 01/10/2025 | ABHIJIT MUKHERJEE | 25.24 | 18.15 | 71.92 | 46
4 | PASCHIM MEDINIPUR | Debra | Midnapore Division | JALIMANDA AND IT'S ADJOINING MOUJAS PWSS | SM/13087 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary wall & Providing Functional Household Tap Connection (15,503 Nos.) including 2 years Operation & Maintenance for Baragarh, Benya, Jalimanda, Malihati, Brindabanpur, Satyapur, Nijpapan, Ashari, Radha Kantapur, Chak Narsingha and Bar Jhikuria Pipe Water Supply Scheme within Debra block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division | ORD/000205/2023-2024 | 2821/MD | 07/08/2023 | 06/10/2025 | GOBINDA MAITY | 4353.07 | 387.41 | 8.9 | 25
Total | [13 empty] | 4411.81 | 405.56 | 9.19