## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Debra | Midnapore Division | KATAI AND IT'S ADJOINING MOUJAS PWSS | SM/13088 | New | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division |  | ORD/000531/2022-2023 | 2192/MD | 01/11/2022 | 30/01/2023 | JADAVPUR UNIVERSITY | 100.36 | 4.78 | 4.76 | 90
2 | PASCHIM MEDINIPUR | Debra | Midnapore Division | KATAI AND IT'S ADJOINING MOUJAS PWSS | SM/13088 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works with laying rising main, distribution system , Sinking of Tube Well , Pump House , Boundary Wall, & Providing Functional Household Tap Connection (6348 Nos) including 2 years operation & maintenance For Chak Sulpan, Katai, Khanamohan, Khamra and Kumarsanda Pipe water supply Scheme within Debra Block Under Kharagpur Sub Division of Midnapore Division PHE Dte. Under Paschim Medinipur District. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE1 Kharagpur Sub-division | ORD/000064/2023-2024 | 2145/MD | 08/06/2023 | 29/04/2026 | GOBINDA MAITY | 1960.6 | 212.34 | 10.83 | 65
3 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | KATAI AND IT'S ADJOINING MOUJAS PWSS | SM/13088 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KATAI AND IT'S ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001757/2022-2023 | 646/W/MMD | 20/03/2023 | 01/01/2026 | PINTU DEY | 21.56 | 13.58 | 62.99 | 90
4 | PASCHIM MEDINIPUR | Debra | Midnapore Division | KATAI AND IT'S ADJOINING MOUJAS PWSS | SM/13088 | New | Material Requisition To Resource Division |  |  | RTOR000009/2023-2024 | 1148/MD | 25/04/2023 | 25/04/2023 | Resource Division | 14.87 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | KATAI AND IT'S ADJOINING MOUJAS PWSS | SM/13088 | New | Electrict quotation bill for TW-II of KATAI pwss (Ref Consumar ID-204251279),Application No-2004649169,Application Type-New Connection,Name of ccc-Balichak ccc, block-Debra. |  |  | BILL/04704/2023-2024 | BP-2023-24-916 | 28/03/2024 | 28/03/2024 | WBSEDCL | 3.51 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | KATAI AND IT'S ADJOINING MOUJAS PWSS | SM/13088 | New | Electrict quotation bill for TW-II of Kotai pwss (Ref Consumar ID-204444965),Application No-2004963042,Application Type-New Connection,Name of CCC-Balichak ccc, block-Debra. |  |  | BILL/03648/2024-2025 | C012539050480 | 21/01/2025 | 21/01/2025 | WBSEDCL | 6.22 | 0 | 0 | 0
Total | [13 empty] | 2107.12 | 230.7 | 10.95