## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Debra | Midnapore Division | KANKRA SIBRAM AND ITS ADJOINING MOUJAS PWSS | SM/13089 | New | Material Requisition To Resource Division |  |  | RTOR000217/2023-2024 | 1514/MD | 12/05/2023 | 12/05/2023 | Resource Division | 21.12 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Debra | Midnapore Division | KANKRA SIBRAM AND ITS ADJOINING MOUJAS PWSS | SM/13089 | New | Construction of 150 Cum & 100 Cum Capacity R.C.C Over Head Reservoir (Intze type with solid raft) with laying rising main, distribution system, Sinking of Tube Well, Pump House & Providing Functional Household Tap Connection (1904 Nos) including 2 years operation & maintenance For Chak Bajit and Kankara Shibram Pipe Water Supply Scheme within Debra Block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division | ORD/000387/2023-2024 | 5061/MD | 26/10/2023 | 25/07/2025 | ANIRUDDHA BAG | 561.96 | 188.62 | 33.57 | 75
3 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | KANKRA SIBRAM AND ITS ADJOINING MOUJAS PWSS | SM/13089 | New | Electrict quotation bill for TW-I of Kanakpur pwss (Ref Consumar ID-204314629),Application No-2004748015,Application Type-New Connection,Name of ccc-Lowada ccc, block-Debra |  |  | BILL/01122/2024-2025 | BP-2024-25-278 | 12/06/2024 | 12/06/2024 | WBSEDCL | 4.62 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | KANKRA SIBRAM AND ITS ADJOINING MOUJAS PWSS | SM/13089 | New | Electrict quotation bill for TW-II of Kanakpur pwss (Ref Consumar ID-204314650),Application No-2004748062,Application Type-New Connection,Name of ccc-Lowada ccc, block-Debra |  |  | BILL/01120/2024-2025 | BP-2024-25-279 | 12/06/2024 | 12/06/2024 | WBSEDCL | 3.21 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | KANKRA SIBRAM AND ITS ADJOINING MOUJAS PWSS | SM/13089 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KANKRA SIBRAM AND ITS ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002045/2022-2023 | 953/W/MMD | 28/03/2023 | 24/09/2023 | MASSK ENGINEERING WORKS | 21.58 | 0 | 0 | 0
Total | [13 empty] | 612.49 | 188.62 | 30.8