## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Keshiary | Central Drilling | KUSUMPUR AND ADJOINING MOUJAS | SM/13093 | New | Providing drilling crew and other allied works for construction of Tube Well (250 mm x 150 mm x 220Mtrs. Depth) by utilising Departmental machineries for Kusumpur W/S Scheme (T/W-I & II) Keshiary Block under Paschim Medinipur District CDD PHE Dte. | Driller In Charge | Junior Engineer | ORD/000039/2023-2024 | 1094/CDD | 18/08/2023 | 17/09/2023 | PADMA ENGINEERING & CO. | 25.33 | 20.55 | 81.12 | 100
2 | PASCHIM MEDINIPUR | Keshiary | Midnapore Division | KUSUMPUR AND ADJOINING MOUJAS | SM/13093 | New | Material Requisition To Resource Division |  |  | RTOR000127/2023-2024 | 1319/MD | 28/04/2023 | 28/04/2023 | Resource Division | 29.75 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | KUSUMPUR AND ADJOINING MOUJAS | SM/13093 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KUSUMPUR AND ADJOINING MOUJASunder JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001427/2023-2024 | 3079/W/MMD | 29/11/2023 | 27/05/2024 | BINAPANI ENTERPRISE | 23.01 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | KUSUMPUR AND ADJOINING MOUJAS | SM/13093 | New | Electric quotation bill for Tw No-I of Kusumpur PWSS. Ref Consumer ID-204136077. |  |  | BILL/02990/2023-2024 | BP-2023-24-385 | 02/12/2023 | 02/12/2023 | WBSEDCL | 3.66 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | KUSUMPUR AND ADJOINING MOUJAS | SM/13093 | New | Electric quotation bill for Tw No-II of Kusumpur PWSS.(Ref Consumer ID-204136080). |  |  | BILL/02991/2023-2024 | BP-2023-24-386 | 02/12/2023 | 02/12/2023 | WBSEDCL | 1.84 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Keshiary | Central Drilling | KUSUMPUR AND ADJOINING MOUJAS | SM/13093 | New | Hiring of Diesel driven motor cab (BS-IV & Above) having contract carriage permit along with driver for the office of the Superintending Engineer, M/E, PMU WBDWSIP P.H.E. Dte. under CMSD-I(D), CDD, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000191/2023-2024 | 291/CMSD-I(D) | 18/12/2023 | 17/06/2024 | SIDDHARTHA CHATTERJEE | 0.89 | 1.72 | 192.93 | 0
Total | [13 empty] | 84.47 | 22.27 | 26.36