## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Keshiary | Midnapore Division | LENGA MARA AND IT'S ADJOINING MOUJAS | SM/13094 | New | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including Sub-Soil investigation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (72023 Nos.) for 41 Nos. PWSS within DANTAN-I, DANTANII & KESHIARY Block Pipe Water Supply Scheme under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II),JE RWS Kharagpur Sub-Division( Keshiary),JE RWS Midnapur Sub-Division( Dantan-I),JE2 Kharagpur Sub Division | ORD/000277/2023-2024 | 5056/MD | 26/10/2023 | 30/06/2026 | ENGINEERING PROJECTS (INDIA) LIMITED | 18003.47 | 90.06 | 0.5 | 30
2 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | LENGA MARA AND IT'S ADJOINING MOUJAS | SM/13094 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for LENGA MARA AND IT'S ADJOINING MOUJASunder JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001426/2023-2024 | 3078/W/MMD | 29/11/2023 | 01/10/2025 | S.P. ENTERPRISE | 22.65 | 15.73 | 69.44 | 20
3 | PASCHIM MEDINIPUR | Keshiary | Central Drilling | LENGA MARA AND IT'S ADJOINING MOUJAS | SM/13094 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm x 150mm x 220 Mtrs.) by utilising departmental rig machine for Langamara PWSS (T/W-I, II & III) Keshiary Block under Pachim Medinipur District, Central Drilling Division PHE Dte. | Driller In Charge | Junior Engineer | ORD/000041/2023-2024 | 1097/CDD | 18/08/2023 | 17/09/2023 | UNIVERSAL ENTERPRISES | 36.91 | 20.14 | 54.56 | 55
4 | PASCHIM MEDINIPUR | Keshiary | Midnapore Division | LENGA MARA AND IT'S ADJOINING MOUJAS | SM/13094 | New | Material Requisition To Resource Division |  |  | RTOR000113/2023-2024 | 1320/MD | 28/04/2023 | 28/04/2023 | Resource Division | 45.8 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | LENGA MARA AND IT'S ADJOINING MOUJAS | SM/13094 | New | Electric quotation bill for Tw No-II of Lengamara PWSS.(Ref Conumer ID-204136078) |  |  | BILL/03021/2023-2024 | BP-2023-24-379 | 02/12/2023 | 02/12/2023 | WBSEDCL | 4.36 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | LENGA MARA AND IT'S ADJOINING MOUJAS | SM/13094 | New | Electric quotation bill for Tw no-I of Langamara PWSS.(Ref Consumer ID-204136076 |  |  | BILL/03020/2023-2024 | BP-2023-24-381 | 02/12/2023 | 02/12/2023 | WBSEDCL | 6.74 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | LENGA MARA AND IT'S ADJOINING MOUJAS | SM/13094 | New | ADDITIONAL QUOTATION FOR NEW SERVICE CONNECTION IRO APPLICATION NO-2004495588, FOR TW NO-II of LANGAMARA PWSS. REF ID-860293842 , APPLICATION TYPE-DEPOSIT WORKS OTHER THAN SERVICE CONNECTION., NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY. |  |  | BILL/04332/2023-2024 | BP-2023-24-810 | 11/03/2024 | 11/03/2024 | WBSEDCL | 1.44 | 0 | 0 | 0
Total | [13 empty] | 18121.37 | 125.92 | 0.69