## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Keshiary | Midnapore Division | MAHISAMURA PWSS | SM/13095 | New | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including Sub-Soil investigation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (72023 Nos.) for 41 Nos. PWSS within DANTAN-I, DANTANII & KESHIARY Block Pipe Water Supply Scheme under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II),JE RWS Kharagpur Sub-Division( Keshiary),JE RWS Midnapur Sub-Division( Dantan-I),JE2 Kharagpur Sub Division | ORD/000277/2023-2024 | 5056/MD | 26/10/2023 | 30/06/2026 | ENGINEERING PROJECTS (INDIA) LIMITED | 18003.47 | 78.09 | 0.43 | 30
2 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | MAHISAMURA PWSS | SM/13095 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for MAHISAMURA PWSSunder JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001425/2023-2024 | 3077/W/MMD | 29/11/2023 | 01/04/2025 | DAS ENTERPRISE | 22.6 | 14.53 | 64.31 | 20
3 | PASCHIM MEDINIPUR | Keshiary | Central Drilling | MAHISAMURA PWSS | SM/13095 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm X150mm X 220 Mtrs. Depth) by utilizing Departmental Machineries for Mahisamura WS Scheme (T/W-l & ll), Keshiary Block under Paschim Medinipur District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000080/2023-2024 | 1095/CDD | 18/08/2023 | 17/09/2023 | UNIVERSAL ENTERPRISES | 25.31 | 21.8 | 86.13 | 100
4 | PASCHIM MEDINIPUR | Keshiary | Midnapore Division | MAHISAMURA PWSS | SM/13095 | New | Material Requisition To Resource Division |  |  | RTOR000131/2023-2024 | 1321/MD | 28/04/2023 | 28/04/2023 | Resource Division | 25.15 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | MAHISAMURA PWSS | SM/13095 | New | ADDITIONAL ELECTRIC QUOTATION BILL FOR TW NO-I OF MAHISHAMURA PWSS DUE TO WAY LEAVE DISPUTE. REF ID-860310382, APPLICATION NO-2004543905, APPLICATION TYPE-DEPOSIT WORKS OTHER THAN SERVICE CONNECTION., NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY |  |  | BILL/02112/2024-2025 | BP-2024-25-624 | 02/09/2024 | 02/09/2024 | WBSEDCL | 3.89 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | MAHISAMURA PWSS | SM/13095 | New | ADDITIONAL ELECTRIC QUOTATION BILL FOR TW NO-II OF MAHISHAMURA PWSS DUE TO WAY LEAVE PROBLEM I.R.O APPLICATION NO-2004578943, APPLICATION TYPE- DEPOSIT WORKS OTHER THAN SERVICE CONNECTION, REFERENCE ID-860304242, APPLICATION ID-100000111812, NAME OF CCC- KESHIARY CCC, BLOCK-KESHIARY. |  |  | BILL/01852/2024-2025 | BP-2024-25-544 | 07/08/2024 | 07/08/2024 | WBSEDCL | 0.81 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | MAHISAMURA PWSS | SM/13095 | New | Electric quotation bill for Tw No-I of Mahisamura PWSS.(Ref Consumer ID-204175254) |  |  | BILL/03331/2023-2024 | BP-2023-24-556 | 16/01/2024 | 16/01/2024 | WBSEDCL | 4.22 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | MAHISAMURA PWSS | SM/13095 | New | ELECTRIC QUOTATION BILL FOR TW NO-II of MAHISHAMURAPWSS. REF CONSUMER ID-204204415, APPLICATION NO-2004578943, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY |  |  | BILL/03577/2023-2024 | BP-2023-24-634 | 08/02/2024 | 08/02/2024 | WBSEDCL | 3.05 | 0 | 0 | 0
Total | [13 empty] | 18088.5 | 114.42 | 0.63