## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | MANIKDIPABARA AND AJOINING MOUJAS PWSS | SM/13097 | New | Material Requisition To Resource Division |  |  | RTOR000104/2023-2024 | 1240/MD | 27/04/2023 | 27/04/2023 | Resource Division | 27.19 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Garbeta-II | Jhargram Mechanical Division | MANIKDIPABARA AND AJOINING MOUJAS PWSS | SM/13097 | New | Payment for WBSEDCL new connection at Manikdipa 2 (SM/13097. MANIKDIPABARA AND ADJOINING MOUJAS PWSS ) |  |  | BILL/00368/2024-2025 | 169/JMD | 07/06/2024 | 07/06/2024 | WBSEDCL | 3.55 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Garbeta-II | Jhargram Mechanical Division | MANIKDIPABARA AND AJOINING MOUJAS PWSS | SM/13097 | New | WBSEDCL new connection payment for Manikdipa t/w 1 |  |  | BILL/00092/2024-2025 | 66/JMD | 29/04/2024 | 29/04/2024 | WBSEDCL | 3.39 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Garbeta-II | Central Drilling | MANIKDIPABARA AND AJOINING MOUJAS PWSS | SM/13097 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
Total | [13 empty] | 21373.9 | 0 | 0