## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | MURAKATA AND ADJOINING MOUJAS PWSS | SM/13100 | New | Material Requisition To Resource Division |  |  | RTOR000034/2023-2024 | 1174/MD | 26/04/2023 | 26/04/2023 | Resource Division | 30.14 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Mechanical | MURAKATA AND ADJOINING MOUJAS PWSS | SM/13100 | New | Quotation for new power connection at Murakata PWSS , Application no - 2004644754 , Ref ID - 204248051 |  |  | BILL/00319/2024-2025 | BP-2024-25-81 | 24/04/2024 | 24/04/2024 | WBSEDCL | 3.11 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Mechanical | MURAKATA AND ADJOINING MOUJAS PWSS | SM/13100 | New | Quotation for new power connection at Murakata PWSS tw- II within Narayangarh block Application No- 2004844779 Ref No - 204369553 |  |  | BILL/02445/2024-2025 | C092443182572 | 27/09/2024 | 27/09/2024 | WBSEDCL | 4.16 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Mechanical | MURAKATA AND ADJOINING MOUJAS PWSS | SM/13100 | New | ELECTRIC QUOTATION BILL FOR TW NO-I of MURAKATA PWSS. REF CONSUMER ID-204204417, APPLICATION NO-2004578935, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY |  |  | BILL/03576/2023-2024 | BP-2023-24-637 | 08/02/2024 | 08/02/2024 | WBSEDCL | 4.64 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Narayangarh | Central Drilling | MURAKATA AND ADJOINING MOUJAS PWSS | SM/13100 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
6 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | MURAKATA AND ADJOINING MOUJAS PWSS | SM/13100 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (5,751 Nos.) including 2 years operation & maintenance For Kunarpur, Murakata & Nayapukur Pipe Water Supply Scheme within Narayangarh block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE2 Kharagpur Sub Division | ORD/000210/2023-2024 | 2827/MD | 07/08/2023 | 24/03/2026 | S & P ENTERPRISE | 1515.85 | 0 | 0 | 15
Total | [13 empty] | 22897.67 | 0 | 0