## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Garbeta-III | Midnapore Division | NALBONA AND ADJOINING MOUJAS PWSS | SM/13101 | New | Material Requisition To Resource Division |  |  | RTOR000077/2023-2024 | 1226/MD | 27/04/2023 | 27/04/2023 | Resource Division | 13.53 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Garbeta-III | Jhargram Mechanical Division | NALBONA AND ADJOINING MOUJAS PWSS | SM/13101 | New | Quotation for new service connection atNalbona T/W-I water supply scheme. |  |  | BILL/00063/2024-2025 | 37/JMD | 29/04/2024 | 29/04/2024 | WBSEDCL | 3.3 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Garbeta-III | Jhargram Mechanical Division | NALBONA AND ADJOINING MOUJAS PWSS | SM/13101 | New | Quotation for new service connection at Nalbona T/W-I water supply scheme. |  |  | BILL/00062/2024-2025 | 36/JMD | 29/04/2024 | 29/04/2024 | WBSEDCL | 3.18 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Garbeta-III | Central Drilling | NALBONA AND ADJOINING MOUJAS PWSS | SM/13101 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
Total | [13 empty] | 21359.77 | 0 | 0