## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Narayangarh | Central Drilling | NAYAPUKUR AND ADJOINING MOUJAS PWSS | SM/13102 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 6.56 | 0.03 | 11
2 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | NAYAPUKUR AND ADJOINING MOUJAS PWSS | SM/13102 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (5,751 Nos.) including 2 years operation & maintenance For Kunarpur, Murakata & Nayapukur Pipe Water Supply Scheme within Narayangarh block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE2 Kharagpur Sub Division | ORD/000210/2023-2024 | 2827/MD | 07/08/2023 | 24/03/2026 | S & P ENTERPRISE | 1515.85 | 118.79 | 7.84 | 15
3 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | NAYAPUKUR AND ADJOINING MOUJAS PWSS | SM/13102 | New | Material Requisition To Resource Division |  |  | RTOR000029/2023-2024 | 1177/MD | 26/04/2023 | 26/04/2023 | Resource Division | 38.98 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Mechanical | NAYAPUKUR AND ADJOINING MOUJAS PWSS | SM/13102 | New | Quotation for new power connection at Nayapukur TW - II within Narayangarh block , Application Id - 2004966089 , Ref ID - 204446079. |  |  | BILL/03261/2024-2025 | C122405716828 | 05/12/2024 | 05/12/2024 | WBSEDCL | 4.06 | 0 | 0 | 0
Total | [13 empty] | 22898.66 | 125.35 | 0.55