## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | PAKURSENI AND ADJOINING MOUJAS PWSS | SM/13104 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Narayangarh Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- (1) Raipur (JL.- 452, Plot-926), (2) Asti (JL.- 706, Plot-496/850), (3) Babalpur (JL.- 350, Plot-876/906), (4) Bahurupa (JL.- 268, Plot-2137), (5) Barakalanki (JL.- 508, Plot-838/1168), (6) Bargopal (JL.- 480, Plot-228/620), (7) Duria (JL.- 583, Plot-686/1639), (8) Gahira (JL.- 727, Plot-1275/1539), (9) Gama (JL.- 545, Plot-532), (10) Govindapur Brahman Saran (JL.- 254, Plot-531/538), (11) Jamuna (JL.- 223, Plot-203), (12) Khursi (JL.- 601, Plot-701/942), (13) Pakurseni (JL.- 520, Plot-608/687), (14) Shuja (JL.- 403, Plot-111/751) & (15) Tutranga (JL.- 671, Plot-897) | AE/RWS Midnapore Sub Division |  | ORD/000597/2022-2023 | 396/MD | 02/02/2023 | 03/05/2023 | JADAVPUR UNIVERSITY | 71.69 | 4.78 | 6.67 | 94
2 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | PAKURSENI AND ADJOINING MOUJAS PWSS | SM/13104 | New | Material Requisition To Resource Division |  |  | RTOR000236/2023-2024 | 1528/MD | 12/05/2023 | 12/05/2023 | Resource Division | 33.2 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Mechanical | PAKURSENI AND ADJOINING MOUJAS PWSS | SM/13104 | New | Quotation for new power connection at Pakurseni PWSS , Application no - 2004644720 , Ref ID - 204248038 |  |  | BILL/04637/2023-2024 | BP-2023-24-896 | 28/03/2024 | 28/03/2024 | WBSEDCL | 3.38 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Mechanical | PAKURSENI AND ADJOINING MOUJAS PWSS | SM/13104 | New | Quotation for new power connection at Pakurseni PWSS T/W - II under Narayangarh block , application no - 2004739517 , ref no - 204309706 |  |  | BILL/01079/2024-2025 | BP-2024-25-233 | 04/06/2024 | 04/06/2024 | WBSEDCL | 4.43 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | PAKURSENI AND ADJOINING MOUJAS PWSS | SM/13104 | New | Sinking of Tube Well, Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Pump House, Boundary Wall & Providing Functional Household Tap Connection (33,066 Nos.) For KASBA NARAYANGARH, KHURSI, NAHARPUR, NARMA, PAKURSENI, ASTI, BARA MAHANPUR, GOBINDAPUR BRAHMAN SASAN, JAMUNA, RERIPUR, TUTRANGA, SHUJANAGAR & GOKULPUR Pipe water supply Scheme within NARAYANGARH Block including 02 (Two) Years Operation & Maintenance Under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE1 Kharagpur Sub-division | ORD/000290/2023-2024 | 5049/MD | 25/10/2023 | 11/06/2026 | SWACH ENVIRONMENT PRIVATE LIMITED | 8498.31 | 214.82 | 2.53 | 41
Total | [13 empty] | 8611.01 | 219.59 | 2.55