## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | PERUABAD AND ADJOINING MOUJAS PWSS | SM/13107 | New | Material Requisition To Resource Division |  |  | RTOR000108/2023-2024 | 1242/MD | 27/04/2023 | 27/04/2023 | Resource Division | 24.38 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Garbeta-II | Jhargram Mechanical Division | PERUABAD AND ADJOINING MOUJAS PWSS | SM/13107 | New | WBSEDCL new connection payment for peruabad t/w 1 |  |  | BILL/00088/2024-2025 | 62/JMD | 29/04/2024 | 29/04/2024 | WBSEDCL | 5.52 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Garbeta-II | Jhargram Mechanical Division | PERUABAD AND ADJOINING MOUJAS PWSS | SM/13107 | New | WBSEDCL new connection payment for Peruabad t/w 2 |  |  | BILL/00089/2024-2025 | 63/JMD | 29/04/2024 | 29/04/2024 | WBSEDCL | 5.59 | 0 | 0 | 0
Total | [13 empty] | 35.49 | 0 | 0