## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | RUPARGHAGRA AND ADJOINING MOUJAS PWSS | SM/13108 | New | Material Requisition To Resource Division |  |  | RTOR000109/2023-2024 | 1243/MD | 27/04/2023 | 27/04/2023 | Resource Division | 19.22 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Garbeta-II | Jhargram Mechanical Division | RUPARGHAGRA AND ADJOINING MOUJAS PWSS | SM/13108 | New | Payment for new service connection charges Ruparghagra T/W-2 |  |  | BILL/00091/2024-2025 | 65/JMD | 29/04/2024 | 29/04/2024 | WBSEDCL | 7.43 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Garbeta-II | Jhargram Mechanical Division | RUPARGHAGRA AND ADJOINING MOUJAS PWSS | SM/13108 | New | Payment for new service connection charges Ruparghagra T/W-1 |  |  | BILL/00090/2024-2025 | 64/JMD | 29/04/2024 | 29/04/2024 | WBSEDCL | 8.29 | 0 | 0 | 0
Total | [13 empty] | 34.94 | 0 | 0