## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Chandrakona-I | Midnapore Mechanical | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GOHALDANGA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. | SM/13111 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GOHALDANGA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001663/2022-2023 | 577/W/MMD | 20/03/2023 | 01/07/2025 | R.S. ENTERPRISE | 12.62 | 8.87 | 70.32 | 60
2 | PASCHIM MEDINIPUR | Chandrakona-I | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GOHALDANGA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. | SM/13111 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 250 & 450 cum OHRs (Intze type) & Accommodate FHTC (4,203 Nos.) under JJM with allied work for (1) Gohaldanga & (2) Haridharpur PWSS in Chandrakona-I Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-I) | ORD/000252/2023-2024 | 3147/MD | 29/08/2023 | 16/08/2025 | BANERJEE CONSTRUCTION | 1062.73 | 0 | 0 | 30
3 | PASCHIM MEDINIPUR | Chandrakona-I | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GOHALDANGA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. | SM/13111 | New | Material Requisition To Resource Division |  |  | RTOR000068/2022-2023 | 89/MD | 10/01/2023 | 10/01/2023 | Resource Division | 6.9 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Chandrakona-I | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GOHALDANGA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. | SM/13111 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at newly proposed T/W no. II of Gohaldanga water supply scheme in the district of Paschim Medinipur under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000739/2024-2025 | 6941/JMD | 13/09/2024 | 12/05/2025 | R S ENTERPRISE | 11.26 | 8.08 | 71.81 | 60
5 | PASCHIM MEDINIPUR | Chandrakona-I | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GOHALDANGA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. | SM/13111 | New | Material Requisition To Resource Division |  |  | RTOR000003/2024-2025 | 3324/MD | 25/11/2024 | 25/11/2024 | Resource Division | 6.78 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Chandrakona-I | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GOHALDANGA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. | SM/13111 | New | Laying of rising main & interconnection for Gohaldanga & its adjoining mouzas PWSS, Block: - Chandrakona-I, District: - Paschim Midnapore under Midnapore Division, PHE Dte. | AE Ghatal Sub-division |  | ORD/000434/2024-2025 | 319/MD | 29/01/2025 | 15/03/2025 | ASHOK BANERJEE | 5.11 | 0 | 0 | 0
Total | [13 empty] | 1105.39 | 16.96 | 1.53