## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | TRIKALPUR AND ADJOINING MOUJAS PWSS | SM/13112 | New | Material Requisition To Resource Division |  |  | RTOR000272/2023-2024 | 3985/MD | 06/10/2023 | 06/10/2023 | Resource Division | 23.4 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | TRIKALPUR AND ADJOINING MOUJAS PWSS | SM/13112 | New | Material Requisition To Resource Division |  |  | RTOR000107/2024-2025 | 3443/MD | 25/11/2024 | 25/11/2024 | Resource Division | 4.68 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Mechanical | TRIKALPUR AND ADJOINING MOUJAS PWSS | SM/13112 | New | Quotation for new power connection at Trikalpur PWSS T/W - I |  |  | BILL/03573/2023-2024 | BP-2023-24-602 | 07/02/2024 | 07/02/2024 | WBSEDCL | 2.74 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Mechanical | TRIKALPUR AND ADJOINING MOUJAS PWSS | SM/13112 | New | Quotation for new power connection at Trikalpur PWSS T/W - II |  |  | BILL/03574/2023-2024 | BP-2023-24-601 | 07/02/2024 | 07/02/2024 | WBSEDCL | 3.55 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Narayangarh | Central Drilling | TRIKALPUR AND ADJOINING MOUJAS PWSS | SM/13112 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 17.54 | 0.08 | 11
6 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | TRIKALPUR AND ADJOINING MOUJAS PWSS | SM/13112 | New | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection 14,471 Nos.) including 2 years operation & maintenance for Radhanagar, Akanda, Kashbaasanda, Kutki, Tarua, Trikalpur, Uttar Karkara and Shashinda Pipe Water Supply Scheme within Narayangarh block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE2 Kharagpur Sub Division | ORD/000212/2023-2024 | 2823/MD | 07/08/2023 | 24/12/2025 | S & P ENTERPRISE | 3925.58 | 156.98 | 4 | 20
Total | [13 empty] | 25299.72 | 174.51 | 0.69