## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Keshiary | Midnapore Division | KULBANI AND ADJOINING MOUJAS PWSS | SM/13121 | New | Material Requisition To Resource Division |  |  | RTOR000126/2023-2024 | 1318/MD | 28/04/2023 | 28/04/2023 | Resource Division | 43.67 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | KULBANI AND ADJOINING MOUJAS PWSS | SM/13121 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KULBANI AND ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001424/2023-2024 | 3076/W/MMD | 29/11/2023 | 27/05/2024 | M/S EMMESS | 34.18 | 0 | 0 | 20
3 | PASCHIM MEDINIPUR | Keshiary | Central Drilling | KULBANI AND ADJOINING MOUJAS PWSS | SM/13121 | New | Providing drilling crew and other allied works for construction of Tube Well ( 250mm X150mm X 220 Mtrs. Depth) by utilizing Departmental Machineries for Kulbani W/S Scheme (T/W-I, II & III), Keshiary Block under Paschim Medinipur District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000090/2023-2024 | 1096/CDD | 18/08/2023 | 17/09/2023 | PADMA ENGINEERING & CO. | 36.93 | 0 | 0 | 60
4 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | KULBANI AND ADJOINING MOUJAS PWSS | SM/13121 | New | ELECTRIC QUOTATION BILL FOR TW NO-II of KULBONI PWSS. REF CONSUMER ID-204226373, APPLICATION NO-2004615869, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY |  |  | BILL/04334/2023-2024 | BP-2023-24-805 | 11/03/2024 | 11/03/2024 | WBSEDCL | 6.65 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | KULBANI AND ADJOINING MOUJAS PWSS | SM/13121 | New | ELECTRIC QUOTATION BILL FOR TW NO-I of KULBONI PWSS. REF CONSUMER ID-204226372, APPLICATION NO-2004615833, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY |  |  | BILL/04333/2023-2024 | BP-2023-24-806 | 11/03/2024 | 11/03/2024 | WBSEDCL | 6.53 | 0 | 0 | 0
Total | [13 empty] | 127.97 | 0 | 0