## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | KUNARPUR AND ADJOINING MOUJAS PWSS | SM/13122 | New | Material Requisition To Resource Division |  |  | RTOR000031/2023-2024 | 1172/MD | 26/04/2023 | 26/04/2023 | Resource Division | 29.08 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Mechanical | KUNARPUR AND ADJOINING MOUJAS PWSS | SM/13122 | New | Quotation for new power connection at Kunarpur PWSS PH - I within Narayangarh Block Application No - 2004909181, Ref ID - 204404487 |  |  | BILL/02968/2024-2025 | C102455616858 | 30/10/2024 | 30/10/2024 | WBSEDCL | 3.69 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Mechanical | KUNARPUR AND ADJOINING MOUJAS PWSS | SM/13122 | New | Quotation for new power connection at Kunarpur PWSS PH - II within Narayangarh Block Application No - 2004909199, Ref ID - 204404484 |  |  | BILL/02967/2024-2025 | C102455618296 | 30/10/2024 | 30/10/2024 | WBSEDCL | 4.96 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | KUNARPUR AND ADJOINING MOUJAS PWSS | SM/13122 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (5,751 Nos.) including 2 years operation & maintenance For Kunarpur, Murakata & Nayapukur Pipe Water Supply Scheme within Narayangarh block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE2 Kharagpur Sub Division | ORD/000210/2023-2024 | 2827/MD | 07/08/2023 | 24/03/2026 | S & P ENTERPRISE | 1515.85 | 94.98 | 6.27 | 15
5 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Mechanical | KUNARPUR AND ADJOINING MOUJAS PWSS | SM/13122 | New | Supply delivery and installation of kit kat fuse carrier for different water supply scheme under Narayangarh Block and others under Midnapore Mechanical Sub Division-I,P.H.E.Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division | ORD/000368/2024-2025 | 1087/MMSD-I | 06/08/2024 | 21/08/2024 | SOUMEN ELECTRIC | 6.62 | 0 | 0 | 50
6 | PASCHIM MEDINIPUR | Narayangarh | Central Drilling | KUNARPUR AND ADJOINING MOUJAS PWSS | SM/13122 | New | Hiring of Diesel driven motor cab (BS-III & Above) having contract carriage permit along with driver for the office of the Calcutta Mechanical Sub-Divn-I(D), C.D.D., P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000011/2025-2026 | 129/CMSD-I | 25/04/2025 | 26/10/2025 | RUPAM GHOSH | 0.87 | 0.72 | 82.78 | 0
Total | [13 empty] | 1561.08 | 95.7 | 6.13