## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Maligram & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | SM/13123 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvination / Augmentation of existing Maligram PWSS Within Pingla Block under Midnapore Division P.H.E. Dte | AE Kharagpur Sub-division |  | ORD/000272/2022-2023 | 547/AE/KSD | 23/08/2022 | 22/09/2022 | GOBINDA MAITY | 3.06 | 3 | 97.96 | 100
2 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Maligram & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | SM/13123 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Based Pipe Water Supply Scheme for Maligram & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001607/2022-2023 | 487/W/MMD | 20/03/2023 | 15/01/2026 | M/S MANABESH ROY | 22.93 | 10.66 | 46.5 | 40
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Maligram & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | SM/13123 | Augmentation | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary wall for Augmentation of Maligram PWSS in Pingla block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE1 Kharagpur Sub-division | ORD/000586/2022-2023 | 297/MD | 24/01/2023 | 16/04/2025 | M/S. D.K.H.CONSTRUCTION | 282.94 | 141.65 | 50.06 | 61
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Maligram & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | SM/13123 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000168/2023-2024 | 1368/MD | 02/05/2023 | 02/05/2023 | Resource Division | 38.07 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Maligram & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | SM/13123 | Augmentation | Quotation for Addl. TW-IV of Maligram W/S Scheme (Consumer ID 203971943) |  |  | BILL/00076/2023-2024 | BP-2023-24-35 | 04/05/2023 | 04/05/2023 | WBSEDCL | 4.08 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Maligram & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | SM/13123 | Augmentation | Additional work in connection of Laying of Distribution pipe line for Augmentation of Maligram Pipe Water Supply Scheme under Pingla Block within Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE1 Kharagpur Sub-division | ORD/000311/2024-2025 | 3404/MD | 25/11/2024 | 23/02/2025 | UTTAM KUMAR DAS | 80.7 | 0 | 0 | 0
Total | [13 empty] | 431.77 | 155.31 | 35.97