## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Keshiary | Midnapore Division | KHARIPARA AND IT'S ADJOINING MOUJAS | SM/13125 | New | Material Requisition To Resource Division |  |  | RTOR000114/2023-2024 | 1317/MD | 28/04/2023 | 28/04/2023 | Resource Division | 25.94 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Keshiary | Central Drilling | KHARIPARA AND IT'S ADJOINING MOUJAS | SM/13125 | New | Providing drilling crew and other allied works for construction of Tube Well ( 250mm X150mm X 220 Mtrs. Depth) by utilizing Departmental Machineries for Kharipara W/S Scheme (T/W-I & II), Keshiary Block under Paschim Medinipur District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000085/2023-2024 | 1093/CDD | 18/08/2023 | 17/09/2023 | M/S B.P.TRADING CORPORATION | 25.33 | 0 | 0 | 100
3 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | KHARIPARA AND IT'S ADJOINING MOUJAS | SM/13125 | New | ELECTRIC QUOTATION BILL FOR TW NO-II OF KHARIPARA PWSS. REFERENCE CONSUMER ID NO-204408594, APPLICATION NO-2004913789, APPLICATION TYPE- NEW CONNECTION, NAME OF CCC- KESHIARY CCC, NAME OF BLOCK- KESHIARY. |  |  | BILL/02981/2024-2025 | C112417261030 | 12/11/2024 | 12/11/2024 | WBSEDCL | 4.59 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | KHARIPARA AND IT'S ADJOINING MOUJAS | SM/13125 | New | ELECTRIC QUOTATION BILL FOR TW NO-I OF KHARIPARA PWSS. REFERENCE CONSUMER ID NO-204408593, APPLICATION NO-2004913778, APPLICATION TYPE- NEW CONNECTION, NAME OF CCC- KESHIARY CCC, NAME OF BLOCK- KESHIARY. |  |  | BILL/02980/2024-2025 | C112417261960 | 12/11/2024 | 12/11/2024 | WBSEDCL | 3.2 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | KHARIPARA AND IT'S ADJOINING MOUJAS | SM/13125 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KHARIPARA AND IT'S ADJOINING MOUJASunder JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001423/2023-2024 | 3075/W/MMD | 29/11/2023 | 01/04/2025 | DAS ENTERPRISE | 22.6 | 0 | 0 | 25
Total | [13 empty] | 81.66 | 0 | 0