## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Narayangarh | Central Drilling | UTATR KARKARA AND ADJOINING MOUJAS PWSS | SM/13129 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 6.56 | 0.03 | 11
2 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | UTATR KARKARA AND ADJOINING MOUJAS PWSS | SM/13129 | New | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection 14,471 Nos.) including 2 years operation & maintenance for Radhanagar, Akanda, Kashbaasanda, Kutki, Tarua, Trikalpur, Uttar Karkara and Shashinda Pipe Water Supply Scheme within Narayangarh block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE2 Kharagpur Sub Division | ORD/000212/2023-2024 | 2823/MD | 07/08/2023 | 24/03/2026 | S & P ENTERPRISE | 3925.58 | 58.24 | 1.48 | 20
3 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | UTATR KARKARA AND ADJOINING MOUJAS PWSS | SM/13129 | New | Material Requisition To Resource Division |  |  | RTOR000279/2023-2024 | 4052/MD | 12/10/2023 | 12/10/2023 | Resource Division | 25.14 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | UTATR KARKARA AND ADJOINING MOUJAS PWSS | SM/13129 | New | Material Requisition To Resource Division |  |  | RTOR000108/2024-2025 | 3444/MD | 25/11/2024 | 25/11/2024 | Resource Division | 5.12 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Mechanical | UTATR KARKARA AND ADJOINING MOUJAS PWSS | SM/13129 | New | Quotation for new power connection at Uttar Karkara PWSS T/W- I ,Narayangarh Block , Application no- 2004683009 , ref. Id - 204276095 |  |  | BILL/00698/2024-2025 | BP-2024-25-151 | 09/05/2024 | 09/05/2024 | WBSEDCL | 7.19 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | UTATR KARKARA AND ADJOINING MOUJAS PWSS | SM/13129 | New | Construction of approach road for 2nd work site of Uttar Karkara Piped Water Supply Scheme within Narayangarh Block under Midnapore Division, PHE Dte. [100 Mtr. Long X 3 Mtr. Width] | Assistant Engineer (HQ) |  | ORD/000006/2025-2026 | 997/AE/HQ/MD | 22/04/2025 | 22/05/2025 | GOURMOHAN DAS | 1.14 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Mechanical | UTATR KARKARA AND ADJOINING MOUJAS PWSS | SM/13129 | New | Quotation for new power connection at Uttar Karkara PWSS , TW - II under Narayangarh Block , Application No - 2005018915 , Ref ID - 204480437 |  |  | BILL/03962/2024-2025 | C022507885048 | 04/02/2025 | 04/02/2025 | WBSEDCL | 2.93 | 0 | 0 | 0
Total | [13 empty] | 25306.86 | 64.8 | 0.26