## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Garbeta-I | Midnapore Division | DHOBABARIA AND ADJOINIONG MOUJAS PWSS | SM/13140 | New | Material Requisition To Resource Division |  |  | RTOR000039/2023-2024 | 1181/MD | 26/04/2023 | 26/04/2023 | Resource Division | 37.9 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Garbeta-I | Jhargram Mechanical Division | DHOBABARIA AND ADJOINIONG MOUJAS PWSS | SM/13140 | New | NEW SERVICE CONNECTION CHARGES AT Dhobaberia TW-II WATER SUPPLY SCHEME |  |  | BILL/00574/2024-2025 | 253/JMD | 10/07/2024 | 10/07/2024 | WBSEDCL | 3.76 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Garbeta-I | Jhargram Mechanical Division | DHOBABARIA AND ADJOINIONG MOUJAS PWSS | SM/13140 | New | NEW SERVICE CONNECTION CHARGES AT Dhobaberia TW-I WATER SUPPLY SCHEME |  |  | BILL/00573/2024-2025 | 252/JMD | 10/07/2024 | 10/07/2024 | WBSEDCL | 4.02 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Garbeta-I | Midnapore Division | DHOBABARIA AND ADJOINIONG MOUJAS PWSS | SM/13140 | New | Route survey & way leave permission along & across of National Highway in Dhobaberiya PWSS under Midnapore Sadar Sub-Division of Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE1 Sadar Sub-division | ORD/000464/2024-2025 | 379/MD | 31/01/2025 | 21/02/2025 | DONA ASSOCIATES | 10.59 | 0 | 0 | 0
Total | [13 empty] | 56.27 | 0 | 0