## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | GAMARIA PIPED WATER SUPPLY SCHEME | SM/13141 | New | Electric Quotation bill for Tw no-I of Gamaria PWSS. (ref Consumer ID-204109025). |  |  | BILL/02901/2023-2024 | BP-2023-24-326 | 03/11/2023 | 03/11/2023 | WBSEDCL | 3.13 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | GAMARIA PIPED WATER SUPPLY SCHEME | SM/13141 | New | Electric quotation bill for Tw no-II of Gamaria PWSS (Ref Consumer ID-204109023) |  |  | BILL/02903/2023-2024 | BP-2023-24-327 | 03/11/2023 | 03/11/2023 | WBSEDCL | 2.73 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | GAMARIA PIPED WATER SUPPLY SCHEME | SM/13141 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for GAMARIA PIPED WATER SUPPLY SCHEME under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001380/2022-2023 | 2391/W/MMD | 31/12/2022 | 29/06/2023 | SUBHASIS ROY | 22.89 | 13.26 | 57.94 | 25
4 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | GAMARIA PIPED WATER SUPPLY SCHEME | SM/13141 | New | Material Requisition To Resource Division |  |  | RTOR000053/2024-2025 | 3373/MD | 25/11/2024 | 25/11/2024 | Resource Division | 9.7 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | GAMARIA PIPED WATER SUPPLY SCHEME | SM/13141 | New | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including Sub-Soil investigation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (16,427 Nos.) for GAMARIA, UTTAR PIASHALA, KHAS JANGAL, ELUNI, GOPAL BANDH, JHETA JAMBONI, KUBIR CHAK & KUSUMDAHARI Pipe Water Supply Scheme within Keshpur Block under Midnapore Sadar Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | ORD/000183/2023-2024 | 2735/MD | 01/08/2023 | 07/01/2026 | M/S. S.S. ENTERPRISE | 5732.3 | 205.02 | 3.58 | 75
6 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | GAMARIA PIPED WATER SUPPLY SCHEME | SM/13141 | New | Laying of rising main & interconnection for Gamaria & its adjoining mouzas PWSS, Block: - Keshpur, District: - Paschim Midnapore under Midnapore Division, PHE Dte. (Length = 2,320 Mtr.) | AE Sadar Sub-division |  | ORD/000413/2024-2025 | 194/MD | 17/01/2025 | 18/03/2025 | M/S. S.S. ENTERPRISE | 13.11 | 0 | 0 | 0
Total | [13 empty] | 5783.87 | 218.28 | 3.77