## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KHANDANGA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. | SM/13167 | New | Material Requisition To Resource Division |  |  | RTOR000045/2022-2023 | 103/MD | 10/01/2023 | 10/01/2023 | Resource Division | 34.55 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Mechanical | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KHANDANGA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. | SM/13167 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KHANDANGA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. under JJM Program under MMD PHE Dte. |  |  | ORD/001920/2022-2023 | 839/W/MMD | 24/03/2023 | 20/09/2023 | SHOVAN KUMAR DAS | 27.39 | 19.55 | 71.38 | 90
3 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KHANDANGA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. | SM/13167 | New | Material Requisition To Resource Division |  |  | RTOR000009/2024-2025 | 3330/MD | 25/11/2024 | 25/11/2024 | Resource Division | 23.3 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Chandrakona-II | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KHANDANGA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. | SM/13167 | New | Quotation for new service connection at Khandanga T/W-II water supply scheme. |  |  | BILL/00879/2024-2025 | 307/JMD | 14/08/2024 | 14/08/2024 | WBSEDCL | 5.56 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Chandrakona-II | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KHANDANGA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. | SM/13167 | New | Quotation for new service connection at Khandanga TW-I water supply scheme. |  |  | BILL/00878/2024-2025 | 306/JMD | 14/08/2024 | 14/08/2024 | WBSEDCL | 6.54 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KHANDANGA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. | SM/13167 | New | Laying of rising main & interconnection for Khandanga & its adjoining mouzas PWSS, Block: - Chandrakona-II, District: - Paschim Midnapore under Midnapore Division, PHE Dte. | AE Ghatal Sub-division |  | ORD/000431/2024-2025 | 317/MD | 29/01/2025 | 15/03/2025 | AMAL DUTTA ROY | 16.19 | 0 | 0 | 0
Total | [13 empty] | 113.53 | 19.55 | 17.22