## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Division | PALASIA AND ADJOINING MOUJAS PWSS | SM/13168 | New | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division |  | ORD/000531/2022-2023 | 2192/MD | 01/11/2022 | 30/01/2023 | JADAVPUR UNIVERSITY | 100.36 | 4.78 | 4.76 | 90
2 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Division | PALASIA AND ADJOINING MOUJAS PWSS | SM/13168 | New | Material Requisition To Resource Division |  |  | RTOR000086/2022-2023 | 196/MD | 16/01/2023 | 16/01/2023 | Resource Division | 7.32 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Division | PALASIA AND ADJOINING MOUJAS PWSS | SM/13168 | New | Material Requisition To Resource Division |  |  | RTOR000125/2024-2025 | 3461/MD | 25/11/2024 | 25/11/2024 | Resource Division | 10.39 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Mechanical | PALASIA AND ADJOINING MOUJAS PWSS | SM/13168 | New | ELECTRIC QUOTATION BILL FOR TW NO-II of PALASIA PWSS. REF CONSUMER ID-204302056, APPLICATION NO-2004723600, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I |  |  | BILL/01020/2024-2025 | BP-2024-25-227 | 31/05/2024 | 31/05/2024 | WBSEDCL | 2.89 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Mechanical | PALASIA AND ADJOINING MOUJAS PWSS | SM/13168 | New | Electric quotation bill for Tw No-I of PALASIA PWSS. (Ref Consumer ID-204205809), APPLICATION NO-2004580481, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, BLOCK-DANTAN-I |  |  | BILL/03572/2023-2024 | BP-2023-24-606 | 07/02/2024 | 07/02/2024 | WBSEDCL | 0.64 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Mechanical | PALASIA AND ADJOINING MOUJAS PWSS | SM/13168 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for PALASIA AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001383/2022-2023 | 2394/W/MMD | 31/12/2022 | 01/09/2025 | DAS ENTERPRISE | 22.83 | 17.93 | 78.52 | 30
Total | [13 empty] | 144.43 | 22.7 | 15.72