## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Division | PUNDRA AND ADJOINING MOUJAS PWSS | SM/13169 | New | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division |  | ORD/000531/2022-2023 | 2192/MD | 01/11/2022 | 30/01/2023 | JADAVPUR UNIVERSITY | 100.36 | 4.78 | 4.76 | 90
2 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Division | PUNDRA AND ADJOINING MOUJAS PWSS | SM/13169 | New | Material Requisition To Resource Division |  |  | RTOR000109/2022-2023 | 210/MD | 16/01/2023 | 16/01/2023 | Resource Division | 18.39 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Division | PUNDRA AND ADJOINING MOUJAS PWSS | SM/13169 | New | Material Requisition To Resource Division |  |  | RTOR000126/2024-2025 | 3462/MD | 25/11/2024 | 25/11/2024 | Resource Division | 11.14 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Mechanical | PUNDRA AND ADJOINING MOUJAS PWSS | SM/13169 | New | Electric quotation bill for Tw No-I of Pundra PWSS (ref Consumer ID-204121973) |  |  | BILL/03123/2023-2024 | BP-2023-24-412 | 09/12/2023 | 09/12/2023 | WBSEDCL | 5.37 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Mechanical | PUNDRA AND ADJOINING MOUJAS PWSS | SM/13169 | New | Electric quotation bill for Tw no-II of PUNDRA PWSS.(Ref Consumer ID-204183610) |  |  | BILL/03344/2023-2024 | BP-2023-24-564 | 16/01/2024 | 16/01/2024 | WBSEDCL | 4.78 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Mechanical | PUNDRA AND ADJOINING MOUJAS PWSS | SM/13169 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for PUNDRA AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001384/2022-2023 | 2395/W/MMD | 31/12/2022 | 29/03/2025 | DAS ENTERPRISE | 22.83 | 14.05 | 61.55 | 30
7 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Division | PUNDRA AND ADJOINING MOUJAS PWSS | SM/13169 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Sinking of Tube Well, Pump House & laying of rising main, Boundary Wall & Providing Functional Household Tap Connection (18944 Nos) including 2 years Operation & Maintenance for ANTRI, PALASIA, BAMAN BIRUA, BAMANDA, GAZIPUR PATNA, PUNDRA, SALIKOTHA & SARANG Pipe water supply Scheme within Dantan-I Block Under Kharagpur Sub Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I) | ORD/000039/2023-2024 | 1355/MD | 02/05/2023 | 03/12/2025 | SWACH ENVIRONMENT PRIVATE LIMITED | 4465.22 | 275.82 | 6.18 | 45
Total | [13 empty] | 4628.09 | 294.65 | 6.37