## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Division | SALIKOTHA AND ADJOINING MOUJAS PWSS | SM/13171 | New | Material Requisition To Resource Division |  |  | RTOR000110/2022-2023 | 206/MD | 16/01/2023 | 16/01/2023 | Resource Division | 22.06 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Division | SALIKOTHA AND ADJOINING MOUJAS PWSS | SM/13171 | New | Material Requisition To Resource Division |  |  | RTOR000127/2024-2025 | 3463/MD | 25/11/2024 | 25/11/2024 | Resource Division | 21.44 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Mechanical | SALIKOTHA AND ADJOINING MOUJAS PWSS | SM/13171 | New | ELECTRIC QUOTATION BILL FOR TW NO-II OF SALIKOTHA PWSS. REF CONSUMER ID-204355062, APPLICATION NO-2004817398, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I |  |  | BILL/01639/2024-2025 | BP-2024-25-480 | 30/07/2024 | 30/07/2024 | WBSEDCL | 0.82 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Mechanical | SALIKOTHA AND ADJOINING MOUJAS PWSS | SM/13171 | New | ELECTRIC QUOTATION BILL FOR TW NO-I of SALIKOTHA PWSS. REF CONSUMER ID-204212538, APPLICATION NO-2004593803, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I |  |  | BILL/03737/2023-2024 | BP-2023-24-692 | 16/02/2024 | 16/02/2024 | WBSEDCL | 7.51 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Mechanical | SALIKOTHA AND ADJOINING MOUJAS PWSS | SM/13171 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for SALIKOTHA AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001924/2022-2023 | 843/W/MMD | 24/03/2023 | 01/08/2025 | SOUMEN ELECTRIC | 27.37 | 0 | 0 | 20
Total | [13 empty] | 79.21 | 0 | 0