## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Division | SOLPOTA AND ADJOINING MOUJAS PWSS | SM/13174 | New | Material Requisition To Resource Division |  |  | RTOR000067/2023-2024 | 1279/MD | 28/04/2023 | 28/04/2023 | Resource Division | 40.33 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Mechanical | SOLPOTA AND ADJOINING MOUJAS PWSS | SM/13174 | New | ELECTRIC QUOTATION BILL FOR TW NO-I of SOLPOTA PWSS. REF CONSUMER ID-204310319 APPLICATION NO-2004739410, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I |  |  | BILL/01021/2024-2025 | BP-2024-25-203 | 28/05/2024 | 28/05/2024 | WBSEDCL | 6.75 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Mechanical | SOLPOTA AND ADJOINING MOUJAS PWSS | SM/13174 | New | ELECTRIC QUOTATION BILL FOR TW NO-II of SOLPOTA PWSS. REF CONSUMER ID-204310435 APPLICATION NO-2004739612, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I |  |  | BILL/01022/2024-2025 | BP-2024-25-204 | 28/05/2024 | 28/05/2024 | WBSEDCL | 6.41 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Mechanical | SOLPOTA AND ADJOINING MOUJAS PWSS | SM/13174 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for SOLPOTA AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I,Sri Sourav Mondal, JE/Midnapur Mechanical Sub-Division- | ORD/001756/2022-2023 | 647/W/MMD | 20/03/2023 | 28/08/2025 | DEY ENTERPRISE | 21.57 | 0 | 0 | 20
Total | [13 empty] | 75.06 | 0 | 0