## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Garbeta-I | Midnapore Division | TELIJANT AND IT'S ADJOINING MOUJAS PWSS | SM/13175 | New | Material Requisition To Resource Division |  |  | RTOR000045/2023-2024 | 1186/MD | 26/04/2023 | 26/04/2023 | Resource Division | 31.65 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Garbeta-I | Jhargram Mechanical Division | TELIJANT AND IT'S ADJOINING MOUJAS PWSS | SM/13175 | New | New service connection charges at Telijhant TW-II water supply scheme |  |  | BILL/00461/2024-2025 | 219/JMD | 21/06/2024 | 21/06/2024 | WBSEDCL | 3.54 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Garbeta-I | Jhargram Mechanical Division | TELIJANT AND IT'S ADJOINING MOUJAS PWSS | SM/13175 | New | New service connection charges at Telijhant TW-I water supply scheme |  |  | BILL/00462/2024-2025 | 220/JMD | 21/06/2024 | 21/06/2024 | WBSEDCL | 3.67 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Garbeta-I | Central Drilling | TELIJANT AND IT'S ADJOINING MOUJAS PWSS | SM/13175 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
Total | [13 empty] | 21378.63 | 0 | 0