## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | AKANDA AND ADJOINING MOUJAS PWSS | SM/13176 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Narayangarh, Dantan-I & Dantan-II Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS: - (A) Narayangarh block- (1) Kasba, (B) Dantan-I block - (1) Birbhadrapur, (2) Menakapur & (3) Benapura, (C) Dantan-II block - (1) Kusumda (Turkakasba)] | AE/RWS Midnapore Sub Division |  | ORD/000733/2022-2023 | 707/MD | 06/03/2023 | 10/04/2023 | JADAVPUR UNIVERSITY | 23.9 | 0 | 0 | 20
2 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | AKANDA AND ADJOINING MOUJAS PWSS | SM/13176 | New | Material Requisition To Resource Division |  |  | RTOR000030/2023-2024 | 1173/MD | 26/04/2023 | 26/04/2023 | Resource Division | 26.77 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | AKANDA AND ADJOINING MOUJAS PWSS | SM/13176 | New | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection 14,471 Nos.) including 2 years operation & maintenance for Radhanagar, Akanda, Kashbaasanda, Kutki, Tarua, Trikalpur, Uttar Karkara and Shashinda Pipe Water Supply Scheme within Narayangarh block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE2 Kharagpur Sub Division | ORD/000212/2023-2024 | 2823/MD | 07/08/2023 | 24/03/2026 | S & P ENTERPRISE | 3925.58 | 0 | 0 | 20
4 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Mechanical | AKANDA AND ADJOINING MOUJAS PWSS | SM/13176 | New | Supply delivery and installation of kit kat fuse carrier for different water supply scheme under Narayangarh Block and others under Midnapore Mechanical Sub Division-I,P.H.E.Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division | ORD/000368/2024-2025 | 1087/MMSD-I | 06/08/2024 | 21/08/2024 | SOUMEN ELECTRIC | 6.62 | 0 | 0 | 50
Total | [13 empty] | 3982.87 | 0 | 0