## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Keshiary | Midnapore Division | AMRA TARYA AND ADJOINING MOUJAS PWSS | SM/13178 | New | Material Requisition To Resource Division |  |  | RTOR000121/2023-2024 | 1307/MD | 28/04/2023 | 28/04/2023 | Resource Division | 23.16 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | AMRA TARYA AND ADJOINING MOUJAS PWSS | SM/13178 | New | ELECTRIC QUOTATION BILL FOR TW NO-I OF AMRA TARYA PWSS. REF CONSUMER ID-204283802, APPLICATION NO-2004695729, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY |  |  | BILL/01158/2024-2025 | BP-2024-25-271 | 12/06/2024 | 12/06/2024 | WBSEDCL | 3.51 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | AMRA TARYA AND ADJOINING MOUJAS PWSS | SM/13178 | New | ELECTRIC QUOTATION BILL FOR TW NO-II OF AMRA TARYA PWSS. REF CONSUMER ID-204283796, APPLICATION NO-2004695723, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY |  |  | BILL/01157/2024-2025 | BP-2024-25-272 | 12/06/2024 | 12/06/2024 | WBSEDCL | 3.24 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Keshiary | Central Drilling | AMRA TARYA AND ADJOINING MOUJAS PWSS | SM/13178 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 11.66 | 0.05 | 11
5 | PASCHIM MEDINIPUR | Keshiary | Midnapore Division | AMRA TARYA AND ADJOINING MOUJAS PWSS | SM/13178 | New | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including Sub-Soil investigation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (72023 Nos.) for 41 Nos. PWSS within DANTAN-I, DANTANII & KESHIARY Block Pipe Water Supply Scheme under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II),JE RWS Kharagpur Sub-Division( Keshiary),JE RWS Midnapur Sub-Division( Dantan-I),JE2 Kharagpur Sub Division | ORD/000277/2023-2024 | 5056/MD | 26/10/2023 | 26/03/2026 | ENGINEERING PROJECTS (INDIA) LIMITED | 18003.47 | 108.19 | 0.6 | 30
Total | [13 empty] | 39373.14 | 119.85 | 0.3