## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Keshiary | Midnapore Division | AMRA TARYA AND ADJOINING MOUJAS PWSS | SM/13178 | New | Material Requisition To Resource Division |  |  | RTOR000121/2023-2024 | 1307/MD | 28/04/2023 | 28/04/2023 | Resource Division | 23.16 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | AMRA TARYA AND ADJOINING MOUJAS PWSS | SM/13178 | New | ELECTRIC QUOTATION BILL FOR TW NO-I OF AMRA TARYA PWSS. REF CONSUMER ID-204283802, APPLICATION NO-2004695729, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY |  |  | BILL/01158/2024-2025 | BP-2024-25-271 | 12/06/2024 | 12/06/2024 | WBSEDCL | 3.51 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | AMRA TARYA AND ADJOINING MOUJAS PWSS | SM/13178 | New | ELECTRIC QUOTATION BILL FOR TW NO-II OF AMRA TARYA PWSS. REF CONSUMER ID-204283796, APPLICATION NO-2004695723, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY |  |  | BILL/01157/2024-2025 | BP-2024-25-272 | 12/06/2024 | 12/06/2024 | WBSEDCL | 3.24 | 0 | 0 | 0
Total | [13 empty] | 29.9 | 0 | 0