## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Garbeta-III | Midnapore Division | AMSOL AND ADJOINING MOUJAS PWSS | SM/13179 | New | Material Requisition To Resource Division |  |  | RTOR000061/2023-2024 | 1204/MD | 26/04/2023 | 26/04/2023 | Resource Division | 22.73 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Garbeta-III | Jhargram Mechanical Division | AMSOL AND ADJOINING MOUJAS PWSS | SM/13179 | New | Quotation for new service connection at Amsol T/W -I water supply scheme. |  |  | BILL/00071/2024-2025 | 45/JMD | 29/04/2024 | 29/04/2024 | WBSEDCL | 4.13 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Garbeta-III | Jhargram Mechanical Division | AMSOL AND ADJOINING MOUJAS PWSS | SM/13179 | New | Quotation for new service connection at AMSOL T/W-II water supply scheme. |  |  | BILL/00230/2024-2025 | 113/JMD | 13/05/2024 | 13/05/2024 | WBSEDCL | 6.12 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Garbeta-III | Central Drilling | AMSOL AND ADJOINING MOUJAS PWSS | SM/13179 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 6.52 | 0.03 | 11
5 | PASCHIM MEDINIPUR | Garbeta-III | Midnapore Division | AMSOL AND ADJOINING MOUJAS PWSS | SM/13179 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including Sub-Soil investigation works for Construction of Over Head Reservoir with laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (1,23,486 Nos.) for 89 Nos. PWSS within GARBETA-I, GARBETA-III, SALBANI & GARBETA-II Block Pipe Water Supply Scheme under Midnapore Sadar Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II),JE RWS Sadar Sub-Division(Garbeta-III),JE1 Sadar Sub-division,JE2 Sadar Sub-division | ORD/000282/2023-2024 | 5091/MD | 30/10/2023 | 19/10/2026 | RMN INFRASTRUCTURES LIMITED | 34739.93 | 91.39 | 0.26 | 40
Total | [13 empty] | 56112.68 | 97.91 | 0.17