## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Keshiary | Midnapore Division | ANAR AND ADJOINING MOUJAS PWSS | SM/13180 | New | Material Requisition To Resource Division |  |  | RTOR000116/2023-2024 | 1308/MD | 28/04/2023 | 28/04/2023 | Resource Division | 32.28 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | ANAR AND ADJOINING MOUJAS PWSS | SM/13180 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for ANAR AND ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001447/2023-2024 | 3074/W/MMD | 29/11/2023 | 27/05/2024 | SANKAR PRASAD DUTTA AND CO | 22.99 | 0 | 0 | 60
3 | PASCHIM MEDINIPUR | Keshiary | Central Drilling | ANAR AND ADJOINING MOUJAS PWSS | SM/13180 | New | Hiring of Diesel Driven Motor cab (BS-III & Above) having contract carriage permit along with driver for the office of The Executive Engineer, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000218/2023-2024 | 165/S&WSD | 19/12/2023 | 19/06/2024 | ASHUTOSH DAS & CO | 0.86 | 0 | 0 | 50
4 | PASCHIM MEDINIPUR | Keshiary | Central Drilling | ANAR AND ADJOINING MOUJAS PWSS | SM/13180 | New | Providing drilling crew and other allied works for construction of Tube Well ( 250mm X150mm X 220 Mtrs. Depth) by utilising Departmental Machineries for ANAR W/S Scheme (T/W-I & II) , Keshiery Block under Paschim Medinipur District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000089/2023-2024 | 388/CDD | 18/05/2023 | 17/06/2023 | KARTICK BAL | 25.4 | 0 | 0 | 100
5 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | ANAR AND ADJOINING MOUJAS PWSS | SM/13180 | New | ELECTRIC QUOTATION BILL TW NO-II of ANAR PWSS. REF CONSUMER ID-204204416, APPLICATION NO-2004578958, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY |  |  | BILL/03584/2023-2024 | BP-2023-24-639 | 08/02/2024 | 08/02/2024 | WBSEDCL | 4.1 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | ANAR AND ADJOINING MOUJAS PWSS | SM/13180 | New | ELECTRIC QUOTATION BILL TW NO-I of ANAR PWSS. REF CONSUMER ID-204204419, APPLICATION NO-2004578966, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY |  |  | BILL/03580/2023-2024 | BP-2023-24-638 | 07/02/2024 | 07/02/2024 | WBSEDCL | 3.13 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Keshiary | Midnapore Division | ANAR AND ADJOINING MOUJAS PWSS | SM/13180 | New | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including Sub-Soil investigation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (72023 Nos.) for 41 Nos. PWSS within DANTAN-I, DANTANII & KESHIARY Block Pipe Water Supply Scheme under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II),JE RWS Kharagpur Sub-Division( Keshiary),JE RWS Midnapur Sub-Division( Dantan-I),JE2 Kharagpur Sub Division | ORD/000277/2023-2024 | 5056/MD | 26/10/2023 | 26/03/2026 | ENGINEERING PROJECTS (INDIA) LIMITED | 18003.47 | 0 | 0 | 30
Total | [13 empty] | 18092.24 | 0 | 0