## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Keshiary | Midnapore Division | PANCHYAR AND ADJOINING MOUJAS PWSS | SM/13216 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Keshiary Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS: - (1) Bhansra (JL.- 138, Plot-455/738), (2) Gaganeshwar (JL.- 154, Plot- 454), (3) Haripura (JL.- 130, Plot-13), (4) Panchyar (JL.- 194, Plot-400), (5) Santrapur (JL.- 57, Plot-218)] | AE Kharagpur Sub-division |  | ORD/000651/2022-2023 | 746/MD | 13/03/2023 | 12/04/2023 | JADAVPUR UNIVERSITY | 23.9 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Keshiary | Midnapore Division | PANCHYAR AND ADJOINING MOUJAS PWSS | SM/13216 | New | Material Requisition To Resource Division |  |  | RTOR000130/2023-2024 | 1322/MD | 28/04/2023 | 28/04/2023 | Resource Division | 28.03 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | PANCHYAR AND ADJOINING MOUJAS PWSS | SM/13216 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for PANCHYAR AND ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001422/2023-2024 | 3073/W/MMD | 29/11/2023 | 27/05/2024 | CONCORD ENGINEERING | 21.56 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Keshiary | Central Drilling | PANCHYAR AND ADJOINING MOUJAS PWSS | SM/13216 | New | Providing Drilling crew and other allied works for construction of Tube well (250mm x 150mm x 220 mtrs. Depth) by utilising Departmental machineries for Panchyar W/S Scheme (TW-I & II), keshiary block under Paschim Midnapur District, CDD PHE Dte. | Driller In Charge | Junior Engineer | ORD/000112/2023-2024 | 1435/CDD | 26/09/2023 | 24/03/2024 | SUNRISE ENGINEERING CORPORATION | 25.25 | 0 | 0 | 100
5 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | PANCHYAR AND ADJOINING MOUJAS PWSS | SM/13216 | New | ELECTRIC QUOTATION BILL FOR TW NO-I of PANCHYAR PWSS. REF CONSUMER ID-204234628, APPLICATION NO-2004627380 APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY |  |  | BILL/04586/2023-2024 | BP-2023-24-891 | 22/03/2024 | 22/03/2024 | WBSEDCL | 3.1 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | PANCHYAR AND ADJOINING MOUJAS PWSS | SM/13216 | New | ELECTRIC QUOTATION BILL FOR TW NO-II of PANCHYAR PWSS. REF CONSUMER ID-204234627, APPLICATION NO-2004627392, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY |  |  | BILL/04582/2023-2024 | BP-2023-24-892 | 21/03/2024 | 21/03/2024 | WBSEDCL | 3.1 | 0 | 0 | 0
Total | [13 empty] | 104.94 | 0 | 0