## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | RADHANAGAR AND ADJOINING MOUJAS PWSS | SM/13217 | New | Material Requisition To Resource Division |  |  | RTOR000113/2022-2023 | 213/MD | 16/01/2023 | 16/01/2023 | Resource Division | 18.54 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | RADHANAGAR AND ADJOINING MOUJAS PWSS | SM/13217 | New | Material Requisition To Resource Division |  |  | RTOR000028/2023-2024 | 1168/MD | 26/04/2023 | 26/04/2023 | Resource Division | 28.05 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Mechanical | RADHANAGAR AND ADJOINING MOUJAS PWSS | SM/13217 | New | Quotation for new power connection at Radhanagar PWSS T/W- I ,Narayangarh Block , Application no- 2004680777 , ref. Id - 204273485 |  |  | BILL/00697/2024-2025 | BP-2024-25-148 | 09/05/2024 | 09/05/2024 | WBSEDCL | 4.23 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Narayangarh | Central Drilling | RADHANAGAR AND ADJOINING MOUJAS PWSS | SM/13217 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 6.22 | 0.03 | 11
5 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | RADHANAGAR AND ADJOINING MOUJAS PWSS | SM/13217 | New | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection 14,471 Nos.) including 2 years operation & maintenance for Radhanagar, Akanda, Kashbaasanda, Kutki, Tarua, Trikalpur, Uttar Karkara and Shashinda Pipe Water Supply Scheme within Narayangarh block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE2 Kharagpur Sub Division | ORD/000212/2023-2024 | 2823/MD | 07/08/2023 | 24/12/2025 | S & P ENTERPRISE | 3925.58 | 61.34 | 1.56 | 20
6 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | RADHANAGAR AND ADJOINING MOUJAS PWSS | SM/13217 | New | Construction of approach road for Head work site of Radhanagar Piped Water Supply Scheme within Narayangarh Block under Midnapore Division, PHE Dte. [200 Mtr. Long X 3 Mtr. Width] | Assistant Engineer (HQ) |  | ORD/000004/2025-2026 | 995/AE/HQ/MD | 22/04/2025 | 22/05/2025 | GOURMOHAN DAS | 2.28 | 0 | 0 | 0
Total | [13 empty] | 25318.45 | 67.56 | 0.27