## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | RAUTARA AND ADJOINING MOUJAS PWSS | SM/13218 | New | Material Requisition To Resource Division |  |  | RTOR000151/2023-2024 | 1270/MD | 28/04/2023 | 28/04/2023 | Resource Division | 24.42 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Salbani | Jhargram Mechanical Division | RAUTARA AND ADJOINING MOUJAS PWSS | SM/13218 | New | New Service Connection Charges for Rautara T/W - I PWSS |  |  | BILL/01027/2024-2025 | 358/JMD | 20/09/2024 | 20/09/2024 | WBSEDCL | 5.17 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Salbani | Central Drilling | RAUTARA AND ADJOINING MOUJAS PWSS | SM/13218 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
Total | [13 empty] | 21369.35 | 0 | 0