## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Keshiary | Midnapore Division | SANTRAPUR AND ADJOINING MOUJAS PWSS | SM/13219 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Keshiary Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS: - (1) Bhansra (JL.- 138, Plot-455/738), (2) Gaganeshwar (JL.- 154, Plot- 454), (3) Haripura (JL.- 130, Plot-13), (4) Panchyar (JL.- 194, Plot-400), (5) Santrapur (JL.- 57, Plot-218)] | AE Kharagpur Sub-division |  | ORD/000651/2022-2023 | 746/MD | 13/03/2023 | 12/04/2023 | JADAVPUR UNIVERSITY | 23.9 | 4.78 | 20 | 0
2 | PASCHIM MEDINIPUR | Keshiary | Midnapore Division | SANTRAPUR AND ADJOINING MOUJAS PWSS | SM/13219 | New | Material Requisition To Resource Division |  |  | RTOR000129/2023-2024 | 1323/MD | 28/04/2023 | 28/04/2023 | Resource Division | 23.2 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Keshiary | Central Drilling | SANTRAPUR AND ADJOINING MOUJAS PWSS | SM/13219 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm X150mm X 220 Mtrs. Depth) by utilizing Departmental Machineries for Santrapur W/S Scheme (TW-I & II), Keshiary Block under PaschimMedinipur District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000115/2023-2024 | 1436/CDD | 26/09/2023 | 23/05/2024 | MENAKA ENTERPRISE | 25.33 | 21.85 | 86.25 | 100
4 | PASCHIM MEDINIPUR | Keshiary | Midnapore Division | SANTRAPUR AND ADJOINING MOUJAS PWSS | SM/13219 | New | Material Requisition To Resource Division |  |  | RTOR000071/2024-2025 | 3417/MD | 25/11/2024 | 25/11/2024 | Resource Division | 12.22 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | SANTRAPUR AND ADJOINING MOUJAS PWSS | SM/13219 | New | ELECTRIC QUOTATION BILL FOR TW NO-I OF SANTRAPUR PWSS. REF CONSUMER ID-204283799, APPLICATION NO-2004695693, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY |  |  | BILL/01155/2024-2025 | BP-2024-25-274 | 12/06/2024 | 12/06/2024 | WBSEDCL | 9.04 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | SANTRAPUR AND ADJOINING MOUJAS PWSS | SM/13219 | New | ELECTRIC QUOTATION BILL FOR TW NO-II OF SANTRAPUR PWSS. REF CONSUMER ID-204283797, APPLICATION NO-2004695677, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY |  |  | BILL/01156/2024-2025 | BP-2024-25-273 | 12/06/2024 | 12/06/2024 | WBSEDCL | 9.04 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | SANTRAPUR AND ADJOINING MOUJAS PWSS | SM/13219 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for SANTRAPUR AND ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001446/2023-2024 | 3072/W/MMD | 29/11/2023 | 02/05/2025 | SANKAR PRASAD DUTTA AND CO | 22.99 | 2.81 | 12.2 | 25
Total | [13 empty] | 125.72 | 29.43 | 23.41