## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Garbeta-III | Midnapore Division | SHAKHA BAI AND ADJOINING MOUJAS PWSS | SM/13220 | New | Material Requisition To Resource Division |  |  | RTOR000079/2023-2024 | 1228/MD | 27/04/2023 | 27/04/2023 | Resource Division | 26.92 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Garbeta-III | Jhargram Mechanical Division | SHAKHA BAI AND ADJOINING MOUJAS PWSS | SM/13220 | New | Quotation for new service connection at Shakhabai T/W-II water supply scheme. |  |  | BILL/00070/2024-2025 | 44/JMD | 29/04/2024 | 29/04/2024 | WBSEDCL | 4.18 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Garbeta-III | Jhargram Mechanical Division | SHAKHA BAI AND ADJOINING MOUJAS PWSS | SM/13220 | New | New Service connection charges. |  |  | BILL/00416/2024-2025 | 196/JMD | 14/06/2024 | 14/06/2024 | WBSEDCL | 10.32 | 0 | 0 | 0
Total | [13 empty] | 41.41 | 0 | 0