## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Garbeta-III | Midnapore Division | ANDHAR NAYAN AND ADJOINING MOUJAS PWSS | SM/13635 | New | Material Requisition To Resource Division |  |  | RTOR000063/2023-2024 | 1212/MD | 27/04/2023 | 27/04/2023 | Resource Division | 53.41 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Garbeta-III | Jhargram Mechanical Division | ANDHAR NAYAN AND ADJOINING MOUJAS PWSS | SM/13635 | New | Quotation for new service connection at Andharnayan T/W-II water supply scheme. |  |  | BILL/00067/2024-2025 | 41/JMD | 29/04/2024 | 29/04/2024 | WBSEDCL | 4.78 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Garbeta-III | Jhargram Mechanical Division | ANDHAR NAYAN AND ADJOINING MOUJAS PWSS | SM/13635 | New | Quotation for new service connection at Anadarnyan T/W-I water supply scheme. |  |  | BILL/00066/2024-2025 | 40/JMD | 29/04/2024 | 29/04/2024 | WBSEDCL | 5.17 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Garbeta-III | Jhargram Mechanical Division | ANDHAR NAYAN AND ADJOINING MOUJAS PWSS | SM/13635 | New | Quotation for new service connection at Andharnayan T/W-III water supply scheme. |  |  | BILL/00065/2024-2025 | 39/JMD | 29/04/2024 | 29/04/2024 | WBSEDCL | 3.22 | 0 | 0 | 0
Total | [13 empty] | 66.58 | 0 | 0