## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | ASTI AND ADJOINING MOUJAS PWSS | SM/13655 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Narayangarh Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- (1) Raipur (JL.- 452, Plot-926), (2) Asti (JL.- 706, Plot-496/850), (3) Babalpur (JL.- 350, Plot-876/906), (4) Bahurupa (JL.- 268, Plot-2137), (5) Barakalanki (JL.- 508, Plot-838/1168), (6) Bargopal (JL.- 480, Plot-228/620), (7) Duria (JL.- 583, Plot-686/1639), (8) Gahira (JL.- 727, Plot-1275/1539), (9) Gama (JL.- 545, Plot-532), (10) Govindapur Brahman Saran (JL.- 254, Plot-531/538), (11) Jamuna (JL.- 223, Plot-203), (12) Khursi (JL.- 601, Plot-701/942), (13) Pakurseni (JL.- 520, Plot-608/687), (14) Shuja (JL.- 403, Plot-111/751) & (15) Tutranga (JL.- 671, Plot-897) | AE/RWS Midnapore Sub Division |  | ORD/000597/2022-2023 | 396/MD | 02/02/2023 | 03/05/2023 | JADAVPUR UNIVERSITY | 71.69 | 4.78 | 6.67 | 94
2 | PASCHIM MEDINIPUR | Narayangarh | Central Drilling | ASTI AND ADJOINING MOUJAS PWSS | SM/13655 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
3 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | ASTI AND ADJOINING MOUJAS PWSS | SM/13655 | New | Sinking of Tube Well, Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Pump House, Boundary Wall & Providing Functional Household Tap Connection (33,066 Nos.) For KASBA NARAYANGARH, KHURSI, NAHARPUR, NARMA, PAKURSENI, ASTI, BARA MAHANPUR, GOBINDAPUR BRAHMAN SASAN, JAMUNA, RERIPUR, TUTRANGA, SHUJANAGAR & GOKULPUR Pipe water supply Scheme within NARAYANGARH Block including 02 (Two) Years Operation & Maintenance Under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE1 Kharagpur Sub-division | ORD/000290/2023-2024 | 5049/MD | 25/10/2023 | 11/06/2026 | SWACH ENVIRONMENT PRIVATE LIMITED | 8498.31 | 0 | 0 | 41
4 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | ASTI AND ADJOINING MOUJAS PWSS | SM/13655 | New | Material Requisition To Resource Division |  |  | RTOR000218/2023-2024 | 1481 | 10/05/2023 | 10/05/2023 | Resource Division | 37.4 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Mechanical | ASTI AND ADJOINING MOUJAS PWSS | SM/13655 | New | Supply delivery and installation of kit kat fuse carrier for different water supply scheme under Narayangarh Block and others under Midnapore Mechanical Sub Division-I,P.H.E.Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division | ORD/000368/2024-2025 | 1087/MMSD-I | 06/08/2024 | 21/08/2024 | SOUMEN ELECTRIC | 6.62 | 0 | 0 | 50
6 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Mechanical | ASTI AND ADJOINING MOUJAS PWSS | SM/13655 | New | Quotation for new power connection at Asti PWSS T/W - I Within Narayangarh Block Application No - 2004987846, Ref ID- 204460783 |  |  | BILL/03868/2024-2025 |  | 24/12/2024 | 24/12/2024 | WBSEDCL | 4.13 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Mechanical | ASTI AND ADJOINING MOUJAS PWSS | SM/13655 | New | Quotation for new power connection at Asti PWSS T/W - II Within Narayangarh Block Application No - 2004987869, Ref ID- 204460781 |  |  | BILL/03867/2024-2025 |  | 24/12/2024 | 24/12/2024 | WBSEDCL | 3.11 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Mechanical | ASTI AND ADJOINING MOUJAS PWSS | SM/13655 | New | Quotation for new power connection at Asti PWSS TW - II with in Narayangarh Block Application No - 2004987869 Ref ID - 204460781 |  |  | BILL/03676/2024-2025 | C012552942218 | 31/01/2025 | 31/01/2025 | WBSEDCL | 3.11 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Mechanical | ASTI AND ADJOINING MOUJAS PWSS | SM/13655 | New | Quotation for new power connection at Asti PWSS TW - I with in Narayangarh Block Application No - 2004987846 Ref ID - 204460783 |  |  | BILL/03675/2024-2025 | C012552957809 | 31/01/2025 | 31/01/2025 | WBSEDCL | 4.13 | 0 | 0 | 0
Total | [13 empty] | 29968.25 | 4.78 | 0.02