## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Garbeta-II | Central Drilling | AMJOR AND ADJOINING MOUJAS PWSS | SM/13707 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | AMJOR AND ADJOINING MOUJAS PWSS | SM/13707 | New | Hire charges of 1 no Motor Cab ( standard ) Commercial with Catalytic Converter attachment with Bharat stage as per prevalent applicable standard compliant new / not old than 30 ( Thirty ) months from the date of 1st. registration on daily hire rate basis for 12 ( Twelve) months only having contract carriage permit for plying with in West Bengal from Regional Transport Authority for the use of the Assistant Engineer, Midnapore Sadar Sub-Division PHE Dte. (Preferably it would be used only for the JJM Programme for Period of 01 year). | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000467/2023-2024 | 487/AE/MSSD | 08/08/2023 | 08/08/2024 | SANJIT SINHA | 1.91 | 2.5 | 131.12 | 0
3 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | AMJOR AND ADJOINING MOUJAS PWSS | SM/13707 | New | Hire charges of 1 no Motor Cab ( standard ) Commercial with Catalytic Converter attachment with Bharat stage as per prevalent applicable standard compliant new / not old than 30 ( Thirty ) months from the date of 1st. registration on daily hire rate basis for 12 ( Twelve) months only having contract carriage permit for plying with in West Bengal from Regional Transport Authority for the use of the Assistant Engineer, Midnapore Sadar Sub-Division under Midnapur Division PHE Dte. (Period From 15.07.2023 to 14.07.2024) Note :- The vehicle will normally engaged on the all working days ,including all exigency duty and normal disaster. The working days might be enhanced as per additional portfolio entrusted to the dedicated officer . no protest by the vehicle owner will be entertained. the vehicle may be called for (24 x 7) in case of any exigency like Covid19, natural cyclone etc. Fuel-HSD=1Litre/12KM Fuel-Mobil-1Litre/500KM | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000186/2023-2024 | 404/AE/MSSD | 14/07/2023 | 14/07/2024 | M/S. ZAMAN ENTERPRISE | 1.79 | 0 | 0 | 0
Total | [13 empty] | 21343.46 | 2.5 | 0.01