## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Belun & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | SM/13709 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvination / Augmentation of existing Belun PWSS Within Pingla Block under Midnapore Division P.H.E. Dte. | AE Kharagpur Sub-division |  | ORD/000275/2022-2023 | 550/AE/KSD | 23/08/2022 | 22/09/2022 | GOBINDA MAITY | 2.26 | 2.26 | 100 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Belun & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | SM/13709 | Augmentation | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary wall, Balance FHTC (127) & Repair of Pump House & or Augmentation of Belun PWSS in Pingla block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE1 Kharagpur Sub-division | ORD/000625/2022-2023 | 450/MD | 13/02/2023 | 02/01/2025 | MASUM ALI KHAN | 55.11 | 40.72 | 73.89 | 100
3 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Belun & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | SM/13709 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Based Pipe Water Supply Scheme for Belun & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001709/2022-2023 | 614/W/MMD | 20/03/2023 | 01/09/2024 | A.K.SIKDAR | 10.79 | 9.93 | 92.01 | 70
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Belun & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | SM/13709 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000172/2023-2024 | 1370/MD | 02/05/2023 | 02/05/2023 | Resource Division | 5.84 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Belun & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | SM/13709 | Augmentation | Electric quotation for Belun PWSS Tube Well-III WS Scheme (Ref. ID 203917727) |  |  | BILL/00397/2022-2023 | BP-2022-23-147 | 27/03/2023 | 27/03/2023 | WBSEDCL | 0.5 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Belun & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | SM/13709 | Augmentation | Laying additional distribution pipe line to accommodate FHTC (200 Nos.) of Belun Pipe Water Supply Scheme within Pingla Block under Midnapore Division, P.H.E. Dte. | AE Kharagpur Sub-division |  | ORD/000479/2024-2025 | 482/MD | 13/02/2025 | 14/04/2025 | NIMAI HAZRA | 17.07 | 0 | 0 | 0
Total | [13 empty] | 91.57 | 52.9 | 57.78