## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | BABAIBASA AND ADJOINING MOUJAS PWSS | SM/13753 | New | Material Requisition To Resource Division |  |  | RTOR000137/2023-2024 | 1253/MD | 28/04/2023 | 28/04/2023 | Resource Division | 19.95 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Salbani | Jhargram Mechanical Division | BABAIBASA AND ADJOINING MOUJAS PWSS | SM/13753 | New | Supply, delivery & fitting fixing of wooden board & Porcelain fuse unit for receiving power from WBSEDCL at Babaibasa & adjacent water supply schemes of Salboni block under JJM progamme under Jhargram Mechanical Division, P.H.E Dte. in the district of Paschim Medinipur. | Driller-In-Charge | Junior Engineer | ORD/000138/2024-2025 | 3783/JMD | 12/07/2024 | 11/08/2024 | MONORANJAN DEY | 3.85 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Salbani | Jhargram Mechanical Division | BABAIBASA AND ADJOINING MOUJAS PWSS | SM/13753 | New | New service connection charges for Babuibasa w/s scheme, t/w no.I |  |  | BILL/00355/2024-2025 | 158/JMD | 31/05/2024 | 31/05/2024 | WBSEDCL | 6.05 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Salbani | Central Drilling | BABAIBASA AND ADJOINING MOUJAS PWSS | SM/13753 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
Total | [13 empty] | 21369.62 | 0 | 0