## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | BABAIBASA AND ADJOINING MOUJAS PWSS | SM/13753 | New | Material Requisition To Resource Division |  |  | RTOR000137/2023-2024 | 1253/MD | 28/04/2023 | 28/04/2023 | Resource Division | 19.95 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Salbani | Jhargram Mechanical Division | BABAIBASA AND ADJOINING MOUJAS PWSS | SM/13753 | New | New service connection charges for Babuibasa w/s scheme, t/w no.I |  |  | BILL/00355/2024-2025 | 158/JMD | 31/05/2024 | 31/05/2024 | WBSEDCL | 6.05 | 0 | 0 | 0
Total | [13 empty] | 26.01 | 0 | 0