## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | BABALPUR AND ADJOINING MOUJAS PWSS | SM/13754 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Narayangarh Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- (1) Raipur (JL.- 452, Plot-926), (2) Asti (JL.- 706, Plot-496/850), (3) Babalpur (JL.- 350, Plot-876/906), (4) Bahurupa (JL.- 268, Plot-2137), (5) Barakalanki (JL.- 508, Plot-838/1168), (6) Bargopal (JL.- 480, Plot-228/620), (7) Duria (JL.- 583, Plot-686/1639), (8) Gahira (JL.- 727, Plot-1275/1539), (9) Gama (JL.- 545, Plot-532), (10) Govindapur Brahman Saran (JL.- 254, Plot-531/538), (11) Jamuna (JL.- 223, Plot-203), (12) Khursi (JL.- 601, Plot-701/942), (13) Pakurseni (JL.- 520, Plot-608/687), (14) Shuja (JL.- 403, Plot-111/751) & (15) Tutranga (JL.- 671, Plot-897) | AE/RWS Midnapore Sub Division |  | ORD/000597/2022-2023 | 396/MD | 02/02/2023 | 03/05/2023 | JADAVPUR UNIVERSITY | 71.69 | 4.78 | 6.67 | 94
2 | PASCHIM MEDINIPUR | Narayangarh | Central Drilling | BABALPUR AND ADJOINING MOUJAS PWSS | SM/13754 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 13.12 | 0.06 | 11
3 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | BABALPUR AND ADJOINING MOUJAS PWSS | SM/13754 | New | Sinking of Tube Well, Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including Sub-Soil investigation works for Construction of Over Head Reservoir with laying distribution system, Pump House, Boundary Wall & Providing Functional Household Tap Connection (16,427 Nos.) including 2 years operation & maintenance for BABALPUR, BAHURUPA, BARAKALANKI, GAMA & GANUA Pipe Water Supply Scheme within Narayangarh Block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE2 Kharagpur Sub Division | ORD/000238/2023-2024 | 3047/MD | 23/08/2023 | 27/04/2026 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 2411.31 | 47.98 | 1.99 | 25
4 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | BABALPUR AND ADJOINING MOUJAS PWSS | SM/13754 | New | Material Requisition To Resource Division |  |  | RTOR000098/2022-2023 | 189/MD | 16/01/2023 | 16/01/2023 | Resource Division | 15.7 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Mechanical | BABALPUR AND ADJOINING MOUJAS PWSS | SM/13754 | New | Supply delivery and installation of kit kat fuse carrier for different water supply scheme under Narayangarh Block and others under Midnapore Mechanical Sub Division-I,P.H.E.Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division | ORD/000368/2024-2025 | 1087/MMSD-I | 06/08/2024 | 21/08/2024 | SOUMEN ELECTRIC | 6.62 | 0 | 0 | 50
6 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | BABALPUR AND ADJOINING MOUJAS PWSS | SM/13754 | New | Material Requisition To Resource Division |  |  | RTOR000110/2024-2025 | 3446/MD | 25/11/2024 | 25/11/2024 | Resource Division | 8.57 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Mechanical | BABALPUR AND ADJOINING MOUJAS PWSS | SM/13754 | New | Quotation for new power connection at Babalpur PWSS T/W - I , Application no- 2004790923, Ref no : 204339889 |  |  | BILL/01581/2024-2025 | C072438232052 | 23/07/2024 | 23/07/2024 | WBSEDCL | 3.57 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Mechanical | BABALPUR AND ADJOINING MOUJAS PWSS | SM/13754 | New | Quotation for new power connection at Babalpur PWSS T/W - II , Application no- 2004790929, Ref no : 204339891 |  |  | BILL/01580/2024-2025 | C072438248345 | 23/07/2024 | 23/07/2024 | WBSEDCL | 2.91 | 0 | 0 | 0
Total | [13 empty] | 23860.12 | 65.87 | 0.28