## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Salbani | Central Drilling | BAGBASA AND ADJOINING MOUJAS PWSS | SM/13805 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 10.09 | 0.05 | 11
2 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | BAGBASA AND ADJOINING MOUJAS PWSS | SM/13805 | New | Laying distribution pipeline & Accommodate FHTC (555 Nos.) under JJM with allied works for Bag Basa & its adjoining mouzas W/S Scheme in Salbani block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-E] | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000099/2023-2024 | 2474/MD | 14/07/2023 | 29/06/2026 | WATER LINK | 81.95 | 34.9 | 42.59 | 50
3 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | BAGBASA AND ADJOINING MOUJAS PWSS | SM/13805 | New | Laying Rising main, Distribution pipeline & Accommodate FHTC (400 Nos.) including 2 years O & M under JJM with allied works for Bag Basa & its adjoining mouzas W/S Scheme in Salbani block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-D] | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000267/2023-2024 | 3241/MD | 11/09/2023 | 29/04/2026 | MIDNAPUR PIPE CONCERN | 132.56 | 67.09 | 50.61 | 20
4 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | BAGBASA AND ADJOINING MOUJAS PWSS | SM/13805 | New | Laying distribution pipeline & Accommodate FHTC (400 Nos.) under JJM with allied works for Bag Basa & its adjoining mouzas W/S Scheme in Salbani block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-F] | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000351/2023-2024 | 4002/MD | 06/10/2023 | 05/12/2023 | SK. MAIDUL ISLAM | 50.44 | 25.33 | 50.21 | 50
5 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | BAGBASA AND ADJOINING MOUJAS PWSS | SM/13805 | New | Sinking of 2 (Two) Nos. Tube well for Bag Basa & its adjoining mouzas PWSS in Salboni block including supply of all labour & materials under Midnapore Sadar Sub-Division of Midnapore Division, P.H.E. Dte. in Paschim Medinipur District. | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000114/2023-2024 | 2515/MD | 18/07/2023 | 17/08/2023 | ANNAPURNA TUBEWELL WORKS | 15.96 | 15.71 | 98.45 | 100
6 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | BAGBASA AND ADJOINING MOUJAS PWSS | SM/13805 | New | Material Requisition To Resource Division |  |  | RTOR000176/2023-2024 | 1359/MD | 02/05/2023 | 02/05/2023 | Resource Division | 55.34 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | BAGBASA AND ADJOINING MOUJAS PWSS | SM/13805 | New | Construction of Pump House & Boundary wall under JJM with allied works for Bag Basa & its adjoining mouzas W/S Scheme in Salbani block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-B] | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000019/2024-2025 | 2037/MD | 01/07/2024 | 25/08/2025 | M/S. INDRAJIT ROY | 26.6 | 12.25 | 46.06 | 10
8 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | BAGBASA AND ADJOINING MOUJAS PWSS | SM/13805 | New | Construction of Pump House under JJM for Bag Basa & its adjoining mouzas W/S Scheme in Salbani block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-A] | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000179/2024-2025 | 3164/MD | 05/10/2024 | 02/02/2025 | A R ENTERPRISE | 7.17 | 5.9 | 82.33 | 80
9 | PASCHIM MEDINIPUR | Salbani | Jhargram Mechanical Division | BAGBASA AND ADJOINING MOUJAS PWSS | SM/13805 | New | New service connection charges for Bagbasa tw-II |  |  | BILL/01311/2023-2024 | 82/JMD | 12/02/2024 | 12/02/2024 | WBSEDCL | 6.09 | 0 | 0 | 0
10 | PASCHIM MEDINIPUR | Salbani | Jhargram Mechanical Division | BAGBASA AND ADJOINING MOUJAS PWSS | SM/13805 | New | New service connection charges for Bagbasa tw-I |  |  | BILL/01303/2023-2024 | 74/JMD | 12/02/2024 | 12/02/2024 | WBSEDCL | 3.54 | 0 | 0 | 0
11 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | BAGBASA AND ADJOINING MOUJAS PWSS | SM/13805 | New | Construction of 200 cum OHR (Intze type with solid raft) & Accommodate FHTC (400 Nos.) under JJM with allied works for Bag Basa & its adjoining mouzas W/S Scheme in Salbani block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-C] | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000509/2024-2025 | 608/MD | 04/03/2025 | 27/02/2026 | KRISHNENDU SEKHAR DAS | 88.98 | 0 | 0 | 0
Total | [13 empty] | 21808.38 | 171.26 | 0.79